## Sheet1
Year | Site Ref | Location | Recommended Actions | Identified Party / RMA | Overall Status | Milestone | Target Date (end of) | Status | 2019-07-31 | Actions | BCC Lead
2016 | 1 | Alum Rock | Assess whether additional gullies are required to allow runoff to drain | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Review maintenance regime to ensure gullies are free from debris | Highway Maintenance and Management Partner | Complete |  |  |  | Over
2016 | 2 | Bartley Green | Investigate the capacity of the Bartley Brook and culvert | Birmingham City Council (LLFA) in partnership with Environment Agency | Complete |  |  |  | Over
|  |  | Develop an updated model of the watercourse through Senneleys Park including the Bartley Brook and other watercourses | Environment Agency in partnership with Birmingham City Council (LLFA) | Complete | Milestone 1: Undertake river survey | 2018-06-01 | Complete | Over
[5 empty] | Complete | Milestone 2: Incorporate river survey into Upper Bourn Brook modelling | 2019-11-01 | Complete | On track
|  |  | Investigate options to manage overland flows | Birmingham City Council (LLFA) | Complete |  |  |  | Over
|  |  | Investigate options for flood mitigation scheme | Environment Agency in partnership with Birmingham City Council (LLFA) | Complete | Milestone 1: Develop partnership and identify funding for modelling study | 2017-05-01 | Complete | Over
[6 empty] | Milestone 2: Integrated modelling to identify mechanism and options | 2020-01-01 | On track | On track
[6 empty] | Milestone 3: Strategic Outline Business Case | 2020-03-01 | On track | On track
|  |  | Develop catchment options across the upper Bourn Brook catchment to manage flooding from all sources. | Birmingham City Council (LLFA), Severn Trent Water and Environment Agency | Complete | Milestone 1: Develop partnership and identify funding for modelling study | 2017-05-01 | Complete | Over
[6 empty] | Milestone 2: Integrated modelling to identify mechanism and options | 2020-01-01 | On track | On track
[6 empty] | Milestone 3: Strategic Outline Business Case | 2020-03-01 | On track | On track
|  |  | Assess the effectiveness of the installed property level resilience measures | Birmingham City Council (Housing) | Complete |  |  |  | Over
2016 | 3 | Bartley Green (Dainton) | Explore the potential for flood mitigation by re-landscaping the garden and improving property drainage | Birmingham City Council (Housing) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Housing to discuss issues | 2017-06-01 | Complete | Over
[6 empty] | Milestone 2: Housing site visit to assess works and obtain quote | 2020-03-01 | On track | On track
|  |  | Develop catchment options across the upper Bourn Brook catchment to manage flooding from all sources | Birmingham City Council (LLFA), Severn Trent Water and Environment Agency | Cancelled - action not relevant to this site |  |  |  | Over
2016 | 4 | Bordesley Green | Review maintenance regime to ensure gullies are free from debris | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Explore the potential for flood mitigation | Birmingham City Council (LLFA) & Home owners | Complete |  |  |  | Over | LLFA to prepare business case for Pretoria Road | RC
2016 | 5 | Bournville | Explore the potential to manage surface water flows within the public open space through SuDS and other measures | Bournville Village Trust | Complete |  |  |  | Over
2016 | 6 | Falcon Lodge | Assess the condition and capacity of the sewer network in the vicinity of Carhampton Road, Glover Road and Churchill Road | Severn Trent Water | Complete | Milestone 1: Review at risk properties and add to register of sewer flooding | 2019-01-01 | Complete | Over | Tim Smith
[5 empty] | On track | Milestone 2: Pre-feasibility assessment of sewer flood risk | 2020-03-01 | On track | On track | Tim Smith
|  |  | Assess the condition and capacity of the highway drainage network to establish if additional gullies are required | Birmingham City Council (LLFA and Highways) | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the Churchill Brook to establish if additional capacity is required | Birmingham City Council (LLFA) | Complete |  |  |  | Over
|  |  | Explore the potential for flood mitigation | Birmingham City Council (LLFA and Housing) | Complete |  |  |  | Over | LLFA to submit Local Levy bid for modelling | RC
2016 | 7 | Four Oaks | Assess the condition and capacity of the sewer network | Severn Trent Water | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the highway drainage network to establish if additional gullies are required | Birmingham City Council (LLFA and Highways) | Complete |  |  |  | Over
|  |  | Explore the potential for flood mitigation measures | Birmingham City Council (LLFA) and Homeowners | Complete |  |  |  | Over
2016 | 8 | Hampstead | Explore the potential for flood mitigation measures | Birmingham City Council (LLFA & Leisure Services) and Homeowners | Complete | Milestone 1: Review potential for Flood Defence Grant funding | 2018-04-01 | Complete | Over
[6 empty] | Milestone 2: Meeting between BCC LLFA & BCC Housing to discuss issues | 2019-02-01 | Complete | Over
[6 empty] | Milestone 3: Review potential to complete work through BCC housing programme | 2020-03-01 | Complete | On track
2016 | 9 | Handsworth Wood - Grestone | Review of maintenance regime for Hilltop Brook | Birmingham City Council (LLFA and Leisure Services) and Riparian Owners | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the Hilltop Brook | Birmingham City Council (LLFA and Leisure Services) | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the sewer network | Severn Trent Water | On track | Milestone 1: Initial investigation to determine impact of sewer flooding | 2020-03-01 | On track | On track | Tim Smith/Ian Shaw
|  |  | Assess potential for future flood storage scheme on Hilltop Brook | Birmingham City Council (LLFA and Leisure) | Complete |  |  |  | Over | LLFA to prepare scheme and costs linked with completion of Silvercroft modelling | RC
2016 | 10 | Handsworth Wood - Silvercroft | Installation of trash screen and review of maintenance regime for Hilltop Brook | Birmingham City Council (Leisure Services) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Leisure to discuss issues | 2019-07-01 | Complete | Over
[6 empty] | Milestone 2: Installation of trash screen | 2020-03-01 | On track | On track | LLFA bid in place for modelling, awaiting outcome of Local Levy Bid | No Action at present
|  |  | Assess the condition and capacity of Hilltop Brook | Birmingham City Council (LLFA and Leisure Services) | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the sewer network | Severn Trent Water | On track | Milestone 1: Initial investigation to determine impact of sewer flooding | 2020-03-01 | On track | On track | Tim Smith/Ian Shaw
2016 | 11 | Harborne - Bourn Brook | Assess the condition and capacity of the sewer network | Severn Trent Water | On track | Milestone 1: Include in Upper Bourn Brook Catchment Study Modelling | 2020-01-01 | On track | On track | Tim Smith/Ian Shaw
|  |  | Investigate reported instances of foul flooding | Severn Trent Water | On track | Milestone 1: Include in Upper Bourn Brook Catchment Study Modelling | 2020-03-01 | On track | On track | Tim Smith/Ian Shaw
|  |  | Assess the condition and capacity of the highway drainage network | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Routine maintenance of the Bourn Brook and maintain capacity of the bridge arch | Environment Agency | Complete |  |  |  | Over
|  |  | Develop catchment options across the upper Bourn Brook catchment to manage flooding from all sources | Birmingham City Council (LLFA), Severn Trent Water and Environment Agency | Complete | Milestone 1: Develop partnership and identify funding for modelling study | 2017-02-01 | Complete | Over
[6 empty] | Milestone 2: Integrated modelling to identify mechanism and options | 2020-01-01 | On track | On track
[6 empty] | Milestone 3: Strategic Outline Business Case | 2020-03-01 | On track | On track
2016 | 12 | Harborne - Fredas Grove | Explore the potential to integrate flood storage within the Golf Course | Birmingham City Council (LLFA) and Harborne Golf Course | Complete |  |  |  | Over
|  |  | Develop catchment options across the upper Bourn Brook catchment to manage flooding from all sources | Birmingham City Council (LLFA) Severn Trent Water and Environment Agency | Complete | Milestone 1: Develop partnership and identify funding for modelling study | 2017-02-01 | Complete | Over
[6 empty] | Milestone 2: Integrated modelling to identify mechanism and options | 2020-01-01 | On track | On track
[6 empty] | Milestone 3: Strategic Outline Business Case | 2020-03-01 | On track | On track
2016 | 13 | Harborne - Queens Park | Implementation of the proposed flood alleviation scheme | Birmingham City Council (Leisure) | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the sewer network | Severn Trent Water | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the highway drainage network | Highway Maintenance and Management Partner | Complete |  |  |  | Over
2016 | 14 | Mere Green | Assess the condition and capacity of the sewer network | Severn Trent Water | Complete | Milestone 1: Review at risk properties and add to register of sewer flooding | 2019-01-01 | Complete | Over | Tim Smith
[6 empty] | Milestone 2: Undertake flow survey | 2019-10-01 | On track | On track | Tim Smith
|  |  | Assess the condition and capacity of the highway drainage network | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Explore the potential for flood mitigation | Birmingham City Council (LLFA), Severn Trent Water and Home owners | Complete | Milestone 2: Put forward Flood Defence Scheme for grant funding in future programme | 2019-03-01 | Complete | Over | Tim Smith
[5 empty] | On track | Milestone 4: Develop business case | 2021-05-01 | On track | On track | Tim Smith
|  |  | Assess the effectiveness of the installed property level resilience measures | Severn Trent Water | Complete |  |  |  | Over
2016 | 15 | Oscott | Investigate options to manage overland flows from the recreation ground | Birmingham City Council (LLFA and Leisure Services) | Complete |  |  |  | Over
|  |  | Explore the potential for flood mitigation | Birmingham City Council (LLFA) and Home owners | Complete |  |  |  | Over
2016 | 16 | Perry Barr | Investigate options to manage overland flows from the Perry Park, including increasing the height of the bund | Birmingham City Council (Leisure Services) | Complete |  |  |  | Over
|  |  | Investigate capacity of Perry Brook culvert and interaction with River Tame defences | Environment Agency | Complete | Milestone 1: LLFA & EA to review available data | 2019-07-01 | Complete | Over
|  |  |  | Environment Agency | On track | Milestone 2: EA to provide level information to LLFA | 2019-12-01 | On track | On track | LLFA to undertake initial assessment and add to PAFS | RC
|  |  |  | Environment Agency | On track | Milestone 3: STW to instruct RPS to develop model and review options | 2020-01-01 | On track
|  |  | Assess the condition of the sewer network in the catchment area | Severn Trent Water | Complete |  |  |  | Over
2016 | 17 | Perry Beeches | Assess the condition and capacity of the sewer network in the catchment area | Severn Trent Water | On track | Milestone 1: Pre-feasibility assessment of sewer flood risk | 2019-10-01 | On track | On track | Tim Smith
|  |  | Construct a hydraulic model to enhance understanding of flooding mechanisms and develop a set of options to mitigate flooding within the area | Birmingham City Council (LLFA) | Complete |  |  |  | Over | LLFA to explore options for further modelling once STW modelling is complete | No Action at present
|  |  | Review maintenance regime to ensure gullies are free from debris | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Fix and maintain the drainage infrastructure from the elevated sections of the M6. | Highways England | Complete |  |  |  | Over
|  |  | Regular inspections of the Perry Brook culverts | Highways England | Complete |  |  |  | Over
|  |  | Regular inspections and maintenance of the open channel through Perry Park | Birmingham City Council (Leisure) | Complete |  |  |  | Over
2016 | 18 | Quinton | Assess the condition and capacity of the sewer network in the catchment area | Severn Trent Water | On track | Milestone 1: Include in Upper Bourn Brook Catchment Study Modelling | 2019-11-01 | On track | On track | Tim Smith
|  |  | Assess the condition and capacity of the culverted Quinton Brook | Birmingham City Council | Complete | Milestone 1: STW to undertake CCTV survey as part of wider works |  | Complete | Over | Tim Smith
[5 empty] | Complete | Milestone 2: Undertake remedial works to the brook. | 2019-11-01 | Complete | On track | Tim Smith
|  |  | Review maintenance regime to ensure gullies are free from debris | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Develop catchment options across the upper Bourn Brook catchment to manage flooding from all sources | Birmingham City Council (LLFA), Severn Trent Water and Environment Agency | Complete | Milestone 1: Develop partnership and identify funding for modelling study | 2017-02-01 | Complete | Over
[6 empty] | Milestone 2: Integrated modelling to identify mechanism and options | 2020-01-01 | On track | On track
[6 empty] | Milestone 3: Strategic Outline Business Case | 2020-03-01 | On track | On track
|  |  |  | Birmingham City Council (LLFA) | Complete |  |  |  | Over
2016 | 19 | Roughley | Assess the condition and capacity of the sewer network in the vicinity of Slade Road and Willmott Road | Severn Trent Water | On track | Milestone 1: Pre-feasibility assessment of sewer flood risk | 2020-03-01 | On track | On track | Tim Smith
|  |  | Assess the condition and capacity of the highway drainage network to establish if additional gullies are required | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Review of maintenance schedule of highway assets (e.g. gullies) | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Explore the potential for flood mitigation measures | Severn Trent Water | On track | Milestone 1: Pre-feasibility assessment of sewer flood risk | 2020-03-01 | On track | On track | Tim Smith
|  |  | Assess the effectiveness of the installed property level resilience measures | Severn Trent Water | Complete |  |  |  | Over
2016 | 20 | Selly Oak - Wood Brook | Continue to explore options for funding contributions towards Bourn Brook scheme | Environment Agency | Complete | Milestone 1: Continue consultations with potential funders | 2019-10-01 | Complete | On track
|  |  | Assess the condition and capacity of the sewer network in the Bristol Road | Severn Trent Water | On track | Milestone 1: Pre-feasibility assessment of sewer flood risk | 2020-03-01 | On track | On track | Tim Smith
|  |  | Assess the condition and capacity of the highway drainage network to establish if additional gullies are required | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Review of maintenance schedule of highway assets (e.g. gullies) | Highway Maintenance and Management Partner | Complete |  |  |  | Over
2016 | 21 | Selly Oak - Eastern Road | Explore the potential for flood mitigation measures | Birmingham City Council (LLFA) and King Edwards School | Complete |  |  |  | Over | LLFA to develop scheme and cost benefit - possible solution bund | RC
|  |  | Develop catchment options across the upper Bourn Brook catchment to manage flooding from all sources | Birmingham City Council (LLFA), Severn Trent Water and Environment Agency | Cancelled - action not relevant to this site |  |  |  | Over
2016 | 22 | Selly Park North | Modification of the private boundary wall and review of maintenance regime in Riverside Drive to accommodate surface water flows | Birmingham City Council (LLFA and Leisure Services) and Homeowners | Complete |  |  |  | Over
|  |  | Implementation of the flood alleviation scheme | Environment Agency, Birmingham City Council (LLFA) and Severn Trent Water | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the sewer network in catchment area | Severn Trent Water | Complete |  |  |  | Over
2016 | 23 | Woodgate Valley | Construct a hydraulic model to enhance understanding of flooding mechanisms and develop a set of options to mitigate flooding within the area | Birmingham City Council (LLFA) | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of the sewer network | Severn Trent Water | On track | Milestone 1: Include in Upper Bourn Brook Catchment Study Modelling | 2019-11-01 | On track | On track | Tim Smith
|  |  | Assess the condition and capacity of the highway drainage | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Review of maintenance schedule of highway assets (e.g. gullies) | Highway Maintenance and Management Partner | Complete |  |  |  | Over
|  |  | Review property level resilience scheme in Bean Croft | Birmingham City Council (LLFA) | Complete |  |  |  | Over
|  |  | Remove blockages and review maintenance regime of unnamed watercourse | Birmingham City Council (Leisure Services) | Complete |  |  |  | Over
|  |  | Develop catchment options across the upper Bourn Brook catchment to manage flooding from all sources | Birmingham City Council (LLFA), Severn Trent Water and Environment Agency | Complete | Milestone 1: Develop partnership and identify funding for modelling study | 2017-02-01 | Complete | Over
[6 empty] | Milestone 2: Integrated modelling to identify mechanism and options | 2020-01-01 | On track | On track
[6 empty] | Milestone 3: Strategic Outline Business Case | 2020-03-01 | On track | On track
2018 | 1 | Acocks Green - Broom Hall Crescent | Assess condition and capacity of sewer network | Severn Trent Water | On track | Milestone 1: Undertake CCTV Surveys | 2019-11-01 | On track | On track | Tim Smith
[6 empty] | Milestone 2: Review existing modelling info and scope up any additional work required | 2019-12-01 | On track | On track
[6 empty] | Milestone 3: Assess performance of sewer system | 2020-03-01 | On track | On track
2018 | 2 | Billesley - Ardencote Road | Explore the potential for community scale flood mitigation | Birmingham City Council (Housing) and Birmingham City Council (LLFA) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Housing to discuss issues | 2019-04-01 | Complete | Over
[5 empty] | Complete | Milestone 2: Undertake cost benefit assessment | 2019-09-01 | Complete | On track | LLFA to develop scheme and cost benefit - possible solution Walls and Gates | DB/RC
[5 empty] | Complete | Milestone 3: Put forward Flood Defence Scheme for grant funding or Local Levy | 2019-09-01 | Complete | On track
2018 | 3 | Bournbrook & Selly Park - Hubert Road | Explore potential for property flood resilience | Birmingham City Council (LLFA) and Property Owners | Complete | Milestone 1: Undertake cost benefit assessment | 2019-12-01 | Complete | On track | LLFA to develop scheme and cost benefit - possible solution PLR to rear of properties | IS/RC
[5 empty] | Complete | Milestone 2: Put forward Flood Defence Scheme for grant funding or advise property owners that they would need to self fund works | 2019-12-01 | Complete | On track
|  |  | Review maintenance schedule for highway assets | Highway Maintenance and Management Partner | Complete |  |  |  | Over
2018 | 4 | Bournbrook & Selly Park - Oakfield Road | Explore potential for property flood resilience | Birmingham City Council (LLFA) and Property Owners | Complete |  |  |  | Over | LLFA to develop scheme and cost benefit - possible solution PLR to one low threshold property, may not be cost beneficial due to affluent area, therefore homeowner may need to pay/contribute | RC
[5 empty] | Complete |  |  |  | Over
2018 | 5 | Bournbrook & Selly Park - Selly Park North | Implementation of flood alleviation scheme | Environment Agency | Complete |  |  |  | Over
|  |  | Review residual flood risk from surface water | Environment Agency | Complete |  |  |  | Over
|  |  | Assess capacity of existing drainage infrastructure | Highway Maintenance and Management Partner | On track | Milestone 1: AMEY to consider extra gullies | 2020-03-01 | On track | On track | John Hastilow
|  |  | Assess condition and capacity of sewer network | Severn Trent Water | On track | Milestone 1: Detailed survey and model verification | 2020-05-01 | On track | On track | Tim smith
2018 | 6 | Bournbrook & Selly Park - Selly Park South | Explore the potential for property flood resilience | Environment Agency and Property Owners | Complete |  |  |  | Over
[5 empty] | On track | Milestone 2: EA to discuss with Mike Adams to manage residual flood risk |  | On track
2018 | 7 | Bournbrook & Selly Park - The Avenues | Assess condition and capacity of local drainage | Property Owners | Complete | Milestone 1: Advice to residents advising of responsibilities | 2019-12-01 | Complete | On track | LLFA to send letter to residents/hold meeting advising that they check and maintain there own private drainage | IS/DB
|  |  | Explore the potential for community scale mitigation | Environment Agency | Complete | Milestone 1: Submit Strategic Outline Business Cases & pursue Local Level funding | 2019-10-01 | Complete | On track
|  |  | Assess condition and capacity of sewer network | Severn Trent Water | Overdue | Milestone 1: |  | Overdue | Over | Tim Smith
2018 | 8 | Bournville & Cotteridge - Laburnum Road | Explore the potential for community scale mitigation | Birmingham City Council (LLFA) | Complete | Milestone 1: Site investigation | 2020-03-01 | Complete | On track | LLFA to explore potential measures to manage overland flow | IS
[5 empty] | On track | Milestone 2: Put forward Flood Defence Scheme for grant funding or Local Levy subject to a cost benefit ratio | 2020-06-01 | On track | On track
2018 | 9 | Brandwood & Kings Heath - Brandwood Cemetery | Assess the condition and capacity of local drainage | Birmingham City Council (Bereavement) | Complete |  |  |  | Over
|  |  | Review of maintenance schedule for local drainage assets | Birmingham City Council (Bereavement) | Complete |  |  |  | Over
|  |  | Explore the potential for community scale mitigation | Birmingham City Council (Bereavement) | Complete | Milestone 1: Identify proposal and funding | 2019-04-01 | Complete | Over
[6 empty] | Milestone 2: Complete flood mitigation works | 2020-12-03 | On track | On track | LLFA to complete works in cemetery | IS/DB
2018 | 10 | Brandwood & Kings Heath - Brandwood Park Road | Explore the potential for community scale mitigation | Birmingham City Council (Housing) | Complete | Milestone 1: Liaison with land owner | 2019-07-01 | Complete | Over |  | DB
[5 empty] | On track | Milestone 2: Undertake cost benefit assessment | 2019-12-01 | On track | On track | LLFA to develop scheme cost and cost benefit assessment - possible solution flood routing into River Rea | DB/RC
[5 empty] | On track | Milestone 3: Put forward Flood Defence Scheme for grant funding or Local Levy | 2020-03-01 | On track | On track
|  |  | Assess the condition and capacity of highway drainage network | Highway Maintenance and Management Partner | Complete | Milestone 1: |  | Complete | Over | John Hastilow
|  |  | Assess condition and capacity of the watercourse | Birmingham City Council (Leisure) | Complete | Milestone 1: Assess condition of trash screen and watercourse channel | 2019-12-01 | Complete
|  |  | Review maintenance regime of the watercourse | Birmingham City Council (Leisure) | Complete | Milestone 1: Establish routine maintenance regime for trash screen | 2019-12-01 | Complete
2018 | 11 | Brandwood & Kings Heath - High Street | Explore the potential for property flood resilience | Birmingham City Council (LLFA) and Property Owners | On track | Milestone 1: Advice to business owners advising measures they can install to protect themselves | 2019-12-01 | On track | On track | LLFA to write to business owners and provide advice about PLR measures they can fund themselves | RC/HY
|  |  | Assess condition and capacity of the highway drainage network | Highway Maintenance and Management Partner | Complete | Milestone 1: |  | Complete | Over | John Hastilow
2018 | 12 | Brandwood & Kings Heath - Newick Grove/Bryndale Avenue | Explore the potential for community scale flood mitigation | Birmingham City Council (LLFA) | Complete |  |  |  | Over | LLFA to develop scheme cost and undertake cost benefit assessment - possible solution flood walls and gates | DB/RC
[5 empty] | Complete |  |  |  | Over
|  |  | Assess condition and capacity of the highway drainage network | Highway Maintenance and Management Partner | Complete | Milestone 1: |  | Complete | Over | John Hastilow
2018 | 13 | Druids Heath & Monyhull - Bayston Road/Kinsey Grove | Explore the potential for community scale flood mitigation | Birmingham City Council (Leisure) | Complete | Milestone 1: Undertake cost benefit assessment | 2020-03-01 | Complete | On track | LLFA to develop scheme cost and undertake cost benefit assessment - possible solution bunding to rear of properties in allotments | IS/RC
[5 empty] | Complete | Milestone 2: Put forward Flood Defence Scheme for grant funding or Local Levy | 2020-04-01 | Complete | On track
2018 | 14 | Druids Heath & Monyhull - Bicknell Croft/Saxelby Close | Explore the potential for catchment wide flood mitigation | Birmingham City Council (LLFA) and Birmingham City Council (Housing) | Complete | Milestone 1: Undertake baseline modelling | 2019-12-01 | Complete | On track | LLFA to develop scheme scope for detailed modelling assessment and prepare Local Levy bid for funding | RC
[5 empty] | On track | Milestone 2: Put forward Flood Defence Scheme for grant funding or Local Levy subject to the findings of the baseline modelling | 2020-03-01 | On track | On track
2018 | 16 | Druids Heath & Monyhull - Rowcroft Covert | Explore the potential for community scale flood mitigation | Birmingham City Council (Housing) and Birmingham City Council (LLFA) | Complete | Milestone 1: Undertake baseline modelling | 2019-12-01 | On track | On track | LLFA to develop scheme cost and undertake cost benefit assessment - possible solution bunding to rear of properties in POS | IS/RC
[5 empty] | On track | Milestone 2: Put forward Flood Defence Scheme for grant funding or Local Levy subject to the findings of the baseline modelling | 2020-06-01 | On track | On track
|  |  | Assess condition and capacity of local drainage | Birmingham City Council (Housing) | Complete |  |  |  | Over
|  |  | Review maintenance schedule of local drainage assets | Birmingham City Council (Housing) | Complete |  |  |  | Over
2018 | 17 | Druids Heath & Monyhull - Sherstone Covert | Explore the potential for property flood resilience | Birmingham City Council (Housing) and Birmingham City Council (LLFA) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Housing to discuss issues | 2019-04-01 | Complete | Over
[6 empty] | Milestone 2: Review potential to complete work through BCC housing programme | 2020-03-01 | On track | On track
2018 | 18 | Edgbaston - Barsham Close | Assess condition and capacity of local drainage | Birmingham City Council (Housing) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Housing to discuss issues | 2019-04-01 | Complete | Over
[5 empty] | Complete | Milestone 2: Site visit to assess potential for addition local drainage and costs | 2019-12-01 | Complete | On track | LLFA to assess cost of drainage works and provide to Housing | DB/IS
[6 empty] | Milestone 3: Housing to review funding opportunities | 2020-03-01 | On track | On track
|  |  | Review maintenance schedule of local drainage assets | Birmingham City Council (Housing) | Complete |  |  |  | Over
2018 | 19 | Erdington - Spring Lane | Assess condition and capacity of the sewer network | Severn Trent Water | On track | Milestone 1: Undertake CCTV Surveys | 2019-11-01 | On track | On track | Tim Smith
[6 empty] | Milestone 2: Review existing modelling info and scope up any additional work required | 2019-12-01 | On track
[6 empty] | Milestone 3: Assess performance of sewer system | 2020-03-01 | On track
2018 | 20 | Hall Green South - Brookwood Avenue | Assess condition and capacity of the watercourse | Birmingham City Council (LLFA) | Complete | Milestone 1: De-silt River Cole adjacent to Brockwood Avenue | 2019-10-01 | Complete | On track
2018 | 21 | Harborne - Bourn Brook | Assess condition and capacity of the watercourse | Birmingham City Council (Leisure) and Birmingham City Council (Housing) | Complete |  |  |  | Over
|  |  | Review maintenance regime for the watercourse | Birmingham City Council (Leisure) and Birmingham City Council (Housing) | Complete |  |  |  | Over
|  |  | Explore the potential for catchment wide flood mitigation | Environment Agency, Birmingham City Council (LLFA) and Severn Trent Water | Complete | Milestone 1: Develop partnership and identify funding for modelling study | 2017-02-01 | Complete | Over
[6 empty] | Milestone 2: Integrated modelling to identify mechanism and options | 2020-01-01 | On track | On track
[6 empty] | Milestone 3: Strategic Outline Business Case | 2020-03-01 | On track | On track
2018 | 22 | Harborne - Clarence Road | Assess the condition and capacity of the highway drainage network | Highway Maintenance and Management Partner | Complete | Milestone 1: |  | Complete | Over | John Hastilow
|  |  | Assess the condition and capacity of local drainage | Midland Heart | Overdue | Milestone 1: |  | Overdue | Over | Midland Heart
|  |  | Explore the potential for property flood resilience | Birmingham City Council (LLFA) and Property Owners | Complete | Milestone 1: Undertake cost benefit assessment | 2019-12-01 | Complete | On track | LLFA to develop scheme cost and undertake cost benefit assessment - possible PLR | RC
[5 empty] | On track | Milestone 2: Put forward Flood Defence Scheme for grant funding or Local Levy | 2020-03-01 | On track | On track
2018 | 23 | Harborne - Mill Farm Road/Cadleigh Gardens/Quinton Road | Assess the condition and capacity of local drainage | Birmingham City Council (Housing) |  |  |  |  | Over
|  |  | Explore the potential for community scale flood mitigation | Birmingham City Council (Leisure) and Birmingham City Council (LLFA) | Complete | Milestone 1: Incorporate into Upper Bourn Brook study | 2019-12-01 | Complete | On track
|  |  | Explore the potential to minimise leaf litter | Birmingham City Council (Housing) | Complete | Milestone 1: Passed to tree officer to review pollarding of tree in Cadleigh Gardens | 2019-12-01 | Complete | On track
|  |  | Explore the potential for catchment wide flood mitigation | Environment Agency, Birmingham City Council (LLFA) and Severn Trent Water | Complete | Milestone 1: Develop partnership and identify funding for modelling study | 2017-02-01 | Complete | Over
[6 empty] | Milestone 2: Integrated modelling to identify mechanism and options | 2020-03-01 | On track | On track
[6 empty] | Milestone 3: Strategic Outline Business Case | 2020-03-01 | On track | On track
2018 | 24 | Harborne - Weather Oaks | Assess the condition and capacity of local drainage | Private Road Owner via management company MetroPM | Complete |  |  |  | Over
|  |  | Review of maintenance regime schedule of local drainage assets | Private Road Owner via management company MetroPM | Complete |  |  |  | Over
|  |  | Explore the potential to minimise leaf litter | Private Road Owner via management company MetroPM | Complete |  |  |  | Over
|  |  | Assess the condition and capacity of local drainage | Birmingham City Council (Housing) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Housing to discuss issues | 2019-04-01 | Complete | Over
[6 empty] | Milestone 2: Site visit to assess potential for addition local drainage and costs | 2019-06-01 | Complete | Over
[6 empty] | Milestone 3: Put forward Flood Defence Scheme for grant funding or Local Levy | 2019-08-01 | Complete
2018 | 25 | Highters Heath - Arundel Road | Assess the capacity of the highway drainage network | Highway Maintenance and Management Partner | Complete | Milestone 1: |  | Complete | Over | John Hastilow
|  |  | Explore the potential for property flood resilience | Birmingham City Council (LLFA) and Property Owners | Complete | Milestone 1: Undertake cost benefit assessment | 2019-09-01 | Complete | On track | LLFA to develop scheme cost and undertake cost benefit assessment - possible PLR | RC
[6 empty] | Milestone 2: Put forward Flood Defence Scheme for grant funding or Local Levy | 2019-09-01 | Complete | On track
2018 | 26 | Highters Heath - Henlow Road/Sladepool Road | Assess the condition and capacity of the highway drainage network | Highway Maintenance and Management Partner | On track | Milestone 1: | 2019-12-01 | On track | On track | John Hastilow
|  |  | Explore the potential for property flood resilience | Birmingham City Council (LLFA) and Property Owners | On track | Milestone 1: Undertake cost benefit assessment in conjunction with community scale flood mitigation assessment | 2019-12-01 | On track | On track
|  |  | Explore the potential for community scale flood mitigation | Birmingham City Council (Leisure) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Leisure to discuss issues | 2019-05-01 | Complete | Over
[6 empty] | Milestone 2: Put forward Local Levy bid for modelling study | 2019-06-01 | Complete | Over | LLFA to await outcome of modelling funding bid | No Action at present
[6 empty] | Milestone 3: Secure Local Levy funding for modelling study | 2019-07-01 | Complete
[5 empty] | On track | Milestone 3: Undertake modelling study | 2020-01-01 | On track | On track
2018 | 27 | Highters Heath - Mountford Close | Review maintenance schedule of highway assets | Highway Maintenance and Management Partner | On track | Milestone 1: | 2019-12-01 | On track | On track | John Hastilow
|  |  | Assess condition and capacity of local drainage | Birmingham City Council (housing | Complete | Milestone 1: Clearance of blocked gullies | 2019-10-01 | Complete
2018 | 28 | Highters Heath - Warstock Road | Assess the condition and capacity of the sewer network | Severn Trent Water | On track | Milestone 1: Assess performance of sewer system | 2020-01-01 | On track | On track | Tim Smith
2018 | 29 | Moseley - Moor Green | Assess the condition and capacity of the highway drainage network | Highway Maintenance and Management Partner | On track | Milestone 1: AMEY to assess the viability on an extra gully or soakaway | 2019-12-01 | On track | On track | John Hastilow
|  |  | Explore the potential for community scale flood mitigation | Birmingham City Council (Leisure) | Complete | Milestone: 1: Identify scope for detailed modelling and assessment | 2019-12-01 | Complete | On track
[6 empty] | Milestone: 2: Bid for funding from Local Levy for detailed modelling and assessment | 2020-03-01 | Complete | On track
[6 empty] | Milestone 3: Secure Local Levy funding for modelling study | 2019-07-01 | Complete
[5 empty] | On track | Milestone 3: Undertake modelling study | 2020-01-01 | On track | On track
2018 | 30 | North Edgbaston - Wadhurst Road | Planning to agree a way forward with developers | Birmingham City Council (Planning) and Avery Fields Community Sports Trust | Complete | Milestone 1: Construct bund to intercept overland flows | 2018-07-01 | Complete | Over | Becky Clarke
[6 empty] | Milestone 2: Infiltration testing to determine soakaway potential at site | 2019-05-01 | Complete | Over
[5 empty] | Complete | Milestone 3: Consultation with Severn Trent Water to agree discharge of drainage to public sewer | 2019-10-01 | Complete
[5 empty] | complete | Milestone 4: Submit revised drainage strategy to planning for approval | 2019-11-01 | Complete
2018 | 32 | Pype Hayes - Tyburn | Review maintenance regime for the watercourse | Birmingham City Council (Leisure) and Birmingham City Council (LLFA) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Allotments to discuss issues | 2019-09-01 | Complete | On track | LLFA to arrange meeting with Berni Wilson | RC
|  |  | Explore the potential for property level flood resilience | Birmingham City Council (LLFA) and Property Owners | On track | Milestone 2: Advice to business owners advising measures they can install to protect themselves | 2019-12-01 | On track | On track | LLFA to send letter to business holders advising then on PLR | RC
2018 | 33 | Quinton - Amersham Close | Assess the condition and capacity of the local drainage | Birmingham City Council (Housing) | Complete |  |  |  | Over
|  |  | Explore the potential for community scale flood mitigation | Birmingham City Council (Housing) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Housing to discuss issues | 2019-04-01 | Complete | Over
[5 empty] | Complete | Milestone 2: Site visit to assess potential for additional local drainage and costs | 2019-12-01 | Complete | On track | LLFA to assess cost of drainage works and provide to Housing | DB/RC
[6 empty] | Milestone 3: Housing to review funding opportunities | 2020-03-01 | On track | On track
2018 | 34 | Sparkhill | Explore the potential for catchment wide flood mitigation | Environment Agency, Birmingham City Council, Solihull Metropolitan Borough Council and Worcestershire County Council | Complete | Milestone 1: Undertaken post flooding survey to inform potential schemes | 2019-03-01 | Complete | Over
[5 empty] | On track | Milestone 2: Assessment of options for future programme 2021 onwards | 2019-10-01 | On track
[6 empty] | Milestone 3: Assess the operational/capacity of the pumps | 2019-12-01 | On track
[6 empty] | Milestone 4: Asset protection team (N.Lote) to report back on optioneering |  | On track
[6 empty] | Milestone 5: Confirm when the river flow monitor is installed at Formans Rd |  | On track
[6 empty] | Milestone 6: EA provide records of flooding to BCC for inclusion on their register |  | On track
[6 empty] | Milestone 6: EA to provide feedback on Community Engagement Pathfinder |  | On track | On track
2018 | 34 | Stirchley - Dell Road | Assess the condition and capacity of the sewer network | Severn Trent Water and Birmingham City Council (LLFA) | Complete | Milestone 1: Undertake survey and site inspection | 2019-08-01 | Complete | On track | Tim Smith
[6 empty] | Milestone 2: Review existing modelling info and scope up any additional work required | 2019-12-01 | On track
[6 empty] | Milestone 3: Assess performance of sewer system | 2020-03-01 | On track
2018 | 36 | Stirchley - Pitcairn Close | Explore the potential for community scale flood mitigation | Birmingham City Council (LLFA) | Complete | Milestone 1: Site Investigation | 2019-06-01 | Complete | Over
[5 empty] | Complete | Milestone 2: Submit Business Case | 2019-08-01 | Complete | On track
[6 empty] | Milestone 3: Deliver community scale mitigation scheme on site | 2020-03-01 | On track | On track | LLFA to deliver scheme | DB/RC
2018 | 37 | Sutton Trinity - Wyndley Lane | Review maintenance schedule of highway assets | Leisure Centre Management | Complete |  |  |  | Over
2018 | 38 | Sutton Vesey - Boldmere Road and Wakefield Close | Assess condition and capacity of the sewer network | Severn Trent Water | Complete | Milestone 1: Pre-feasibility study to be commissioned and completed | 2019-03-01 | Complete | Over | Tim Smith
[5 empty] | On track | Milestone 2: | 2020-06-01 | On track | On track
|  |  | Assess condition and capacity of local drainage | Highway Maintenance and Management Partner | Complete | Milestone 1: |  | Complete | Over | John Hastilow
2018 | 39 | Druids Heath & Monyhull - Chanston Avenue | Explore the potential for community scale mitigation | Birmingham City Council (Bereavement) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Bereavement to discuss issues | 2019-12-01 | Complete
|  |  | Explore the potential for property level flood resilience | Birmingham City Council (LLFA) and Property Owners | Complete | Milestone 1: Meeting between BCC LLFA and property owner | 2019-12-01 | Complete
|  |  | Assess condition and capacity of the sewer network | Severn Trent Water | On track | Milestone 1: Assess performance of sewer system | 2020-03-01 | On track
2018 | 40 | Druids Heath & Monyhull - Marsham Road | Assess condition and capacity of local drainage | Highway Maintenance and Management Partner | On track | Milestone 1: | 2020-03-01 | On track | On track | John Hastilow
2018 | 41 | Hall Green - Sarehole Road | Assess condition and capacity of the watercourse | Birmingham City Council (Leisure) | Complete | Milestone 1: Meeting between BCC LLFA & BCC Leisure to discuss issues | 2019-08-01 | Complete | On track | John Hastilow
[5 empty] | Complete | Milestone 2: Undertake localised desilting work to River Cole | 2019-12-01 | Complete
Action Progress Summary
|  |  |  | Complete | 139
|  |  |  | On track | 38
|  |  |  | Overdue/No Milestone Set | 2
|  |  |  | Cancelled | 2
Action Progress Summary - Birmingham City Council
|  |  |  | Complete | 81
|  |  |  | On track | 3
|  |  |  | Overdue/No Milestone Set | 0
Action Progress Summary - Environment Agency
|  |  |  | Complete | 19
|  |  |  | On track | 2
|  |  |  | Overdue/No Milestone Set | 0
Action Progress Summary - Severn Trent Water
|  |  |  | Complete | 19
|  |  |  | On track | 15
|  |  |  | Overdue/No Milestone Set | 1
Action Progress Summary - Highway Maintenance and Management Partner
|  |  |  | Complete | 25
|  |  |  | On track | 5
|  |  |  | Overdue/No Milestone Set | 0

## Sheet2
Year | Area | Site Name as in Column O (Copy Flooded tab) linked | Recommended Action | Identified Party / RMA2
2018 | 1 | Acocks Green - Broom Hall Crescent | Assess condition and capacity of sewer network | STW
2018 | 1 |  | Assess condition and capacity of highway drainage network | HM&MP | Complete | #REF!
2018 | 2 | Billesley - Ardencote | Explore the potential for community scale flood mitigation | BCC | On track | #REF!
2018 | 2 |  | Explore the potential for community scale flood mitigation | BCC | Overdue | #REF!
2018 | 3 | Bournbrook & Selly Park - Hubert/Heeley | Explore potential for property flood resilience | BCC | Cancelled | #REF!
2018 | 3 |  | Explore potential for property flood resilience | Property Owners
2018 | 3 |  | Review maintenance schedule for highway assets | HM&MP
2018 | 4 | Bournbrook & Selly Park - Oakfield | Explore potential for property flood resilience | BCC
2018 | 4 |  | Explore potential for property flood resilience | Property Owners
2018 | 5 | Bournbrook & Selly Park - Selly Park North | Implementation of flood alleviation scheme | EA
2018 | 5 |  | Review residual flood risk from surface water | EA
2018 | 5 |  | Assess capacity of existing drainage infrastructure | HM&MP
2018 | 6 | Bournbrook & Selly Park - Selly Park South | Explore the potential for property flood resilience | EA
2018 | 6 |  | Explore the potential for property flood resilience | Property Owners
2018 | 7 | Bournbrook & Selly Park - The Avenues | Assess condition and capacity of local drainage | Property Owners
2018 | 7 |  | Explore the potential for community scale mitigation | EA
2018 | 8 | Bournville & Cotteridge - Laburnum | Explore the potential for community scale mitigation | BCC
2018 | 9 | Brandwood & Kings Heath - Brandwood Cemetery | Assess the condition and capacity of local drainage | BCC
2018 | 9 |  | Review of maintenance schedule for local drainage assets | BCC
2018 | 9 |  | Explore the potential for community scale mitigation | BCC
2018 | 10 | Brandwood & Kings Heath - Brandwood Park | Explore the potential for community scale mitigation | BCC
2018 | 10 |  | Assess the condition and capacity of highway drainage network | HM&MP
2018 | 11 | Brandwood & Kings Heath - High Street | Explore the potential for property flood resilience | BCC
2018 | 11 |  | Explore the potential for property flood resilience | Property Owners
2018 | 11 |  | Assess condition and capacity of the highway drainage network | HM&MP
2018 | 12 | Brandwood & Kings Heath - Newick/Bryndale | Explore the potential for community scale flood mitigation | BCC
2018 | 12 |  | Assess condition and capacity of the highway drainage network | HM&MP
2018 | 13 | Druids Heath & Monyhull - Bayston/Kinsey | Explore the potential for community scale flood mitigation | BCC
2018 | 14 | Druids Heath & Monyhull - Beckfield | Explore the potential for catchment wide flood mitigation | BCC
2018 | 14 |  | Explore the potential for catchment wide flood mitigation | BCC
2018 | 15 | Druids Heath & Monyhull - Pettitt/Garratts | No further actions are recommended for this area. | No further actions
2018 | 16 | Druids Heath & Monyhull - Rowcroft | Explore the potential for community scale flood mitigation | BCC
2018 | 16 |  | Explore the potential for community scale flood mitigation | BCC
2018 | 16 |  | Assess condition and capacity of local drainage | BCC
2018 | 16 |  | Review maintenance schedule of local drainage assets | BCC
2018 | 17 | Druids Heath & Monyhull - Sherston | Explore the potential for property flood resilience | BCC
2018 | 17 |  | Explore the potential for property flood resilience | BCC
2018 | 18 | Edgbaston - Barsham | Assess condition and capacity of local drainage | BCC
2018 | 18 |  | Review maintenance schedule of local drainage assets | BCC
2018 | 19 | Erdington - Spring Lane | Assess condition and capacity of the sewer network | STW
2018 | 20 | Hall Green South - Brookwood | Assess condition and capacity of the watercourse | BCC
2018 | 21 | Harborne - Bourn Brook | Assess condition and capacity of the watercourse | EA
2018 | 21 |  | Assess condition and capacity of the watercourse | BCC
2018 | 21 |  | Assess condition and capacity of the watercourse | BCC
2018 | 21 |  | Review maintenance regime for the watercourse | EA
2018 | 21 |  | Review maintenance regime for the watercourse | BCC
2018 | 21 |  | Review maintenance regime for the watercourse | BCC
2018 | 21 |  | Explore the potential for catchment wide flood mitigation | EA
2018 | 21 |  | Explore the potential for catchment wide flood mitigation | BCC
2018 | 21 |  | Explore the potential for catchment wide flood mitigation | STW
2018 | 22 | Harborne - Clarence | Assess the condition and capacity of the highway drainage network | HM&MP
2018 | 22 |  | Assess the condition and capacity of local drainage | Private Road Owner
2018 | 22 |  | Explore the potential for property flood resilience | BCC
2018 | 22 |  | Explore the potential for property flood resilience | Property Owners
2018 | 23 | Harborne - Mill Farm/Cadleigh | Assess the condition and capacity of local drainage | BCC
2018 | 23 |  | Explore the potential for community scale flood mitigation | BCC
2018 | 23 |  | Explore the potential for community scale flood mitigation | BCC
2018 | 23 |  | Explore the potential to minimise leaf litter | BCC
2018 | 23 |  | Explore the potential for catchment wide flood mitigation | EA
2018 | 23 |  | Explore the potential for catchment wide flood mitigation | BCC
2018 | 23 |  | Explore the potential for catchment wide flood mitigation | STW
2018 | 24 | Harborne - Weather Oaks | Assess the condition and capacity of local drainage | Private Road Owner via management company MetroPM
2018 | 24 |  | Review of maintenance regime schedule of local drainage assets | Private Road Owner via management company MetroPM
2018 | 24 |  | Explore the potential to minimise leaf litter | Private Road Owner via management company MetroPM
2018 | 24 |  | Assess the condition and capacity of local drainage | BCC
2018 | 25 | Highters Heath - Arundel | Assess the capacity of the highway drainage network | HM&MP
2018 | 25 |  | Explore the potential for property flood resilience | BCC
2018 | 25 |  | Explore the potential for property flood resilience | Property Owners
2018 | 26 | Highters Heath - Henlow | Assess the condition and capacity of the highway drainage network | HM&MP
2018 | 26 |  | Explore the potential for property flood resilience | BCC
2018 | 26 |  | Explore the potential for property flood resilience | Property Owners
2018 | 26 |  | Explore the potential for community scale flood mitigation | BCC
2018 | 27 | Highters Heath - Mountford | Review maintenance schedule of highway assets | HM&MP
2018 | 28 | Highters Heath - Grendon/Warstock | Assess the condition and capacity of the sewer network | STW
2018 | 29 | Moseley - Moor Green | Assess the condition and capacity of the highway drainage network | HM&MP
2018 | 29 |  | Assess the condition and capacity of the highway drainage network | BCC
2018 | 29 |  | Explore the potential for community scale flood mitigation | BCC
2018 | 30 | North Edgbaston - Wadhurst | Planning to agree a way forward with developers | BCC
2018 | 30 |  | Planning to agree a way forward with developers | Avery Fields Community Sports Trust
2018 | 31 | Oscott - Queslett | Assess the condition and capacity of local drainage | BCC
2018 | 32 | Pype Hayes - Tyburn | Review maintenance regime for the watercourse | BCC
2018 | 32 |  | Review maintenance regime for the watercourse | BCC
2018 | 32 |  | Explore the potential for property level flood resilience | BCC
2018 | 33 |  | Explore the potential for property level flood resilience | Property Owners
2018 | 33 | Quinton - Overdale/Amersham | Assess the condition and capacity of the local drainage | BCC
2018 | 33 |  | Explore the potential for community scale flood mitigation | BCC
2018 | 34 | Sparkhill | Explore the potential for catchment wide flood mitigation | EA
2018 | 34 | Stirchley - Dell | Assess the condition and capacity of the sewer network | STW
2018 | 34 |  | Explore the potential for community scale flood mitigation | BCC
2018 | 36 | Stirchley - Pitcairn /Falkland | Explore the potential for community scale flood mitigation | BCC
2018 | 37 | Sutton Trinity - Wyndley Lane | Review maintenance schedule of highway assets | Leisure Centre Management
2018 | 38 | Sutton Vesey - Boldmere | Assess condition and capacity of the sewer network | STW
2018 | 38 |  | Assess condition and capacity of local drainage | HM&MP
2018 | 38 |  | Explore the potential for property flood resilience | BCC
2018 | 38 |  | Explore the potential for property flood resilience | Property Owners
2018 | 39 | Sutton Vesey - Wakefield | Assess condition and capacity of the sewer network | STW
2018 | 39 |  | Explore the potential for property flood resilience | BCC
2018 | 39 |  | Explore the potential for property flood resilience | Property Owners