## Sheet1
Scheme Ref no | Road | Start | Finish | Comments
BHHMS-0514 | Middle Leaford | 2022-10-03 | 2022-10-13 | Complete
BHMMS-0512 | Turves Green | 2022-10-03 | 2022-10-11 | Complete | Key
BHMMS-0511 | Teal Drive | 2022-10-06 | 2022-10-07 | Complete | Night Works
BHMMS-0513 | Whitacre Road | 2022-10-17 | 2022-10-25 | Complete | Deferred
BHMMS-0522 | Sommerfield Road | 2022-10-26 | 2022-11-15 | Complete
BHMMS-0521 | Ruthall Close | 2022-11-03 | 2022-11-04 | Complete
BHMMS-0523 | Stoney Lane | 2022-11-15 | 2022-11-22 | Complete
BHMMS-0541 | Redhill Road | 2022-11-18 | 2022-12-02 | Complete
BHMMS-0548 | Rubery Lane | 2023-01-06 | 2023-01-16 | Complete
BHMMS-0547 | Park Way | 2023-01-17 | 2023-02-10 | Complete
BHMMS-0542 | Long Acre | 2023-02-01 | 2023-02-28 | Complete
BHMMS-0549 | Homer Road | 2023-02-27 | 2023-03-02 | Complete
BHMMS-0427 | Woodgate Lane | 2023-03-27 | 2023-03-31 | Complete
BHMMS-0530A | Green Acres Road, Kings Norton | 2023-06-05 | 2023-06-12 | Complete
BHMMS-0364 | Yardley Wood Road | 2023-06-12 | 2023-07-21 | Complete
BHMMS-0530C | The Mount | 2023-06-13 | 2023-06-15 | Complete
BHMMS-0500 | Cartland Road | 2023-07-20 | 2023-08-29 | Complete
LSRMS/CW/79 | Grosvenor Street West | 2023-07-29 | 2023-08-30 | Complete
BHMMS-0530D | Dyas Ave, Perry Barr | 2023-09-04 | 2023-09-13 | Complete
LSRMS/CW/120 | Ingham Way | 2023-11-13 | 2023-11-13 | Complete
BHMMS-0530E | Holly Lane, Pype Hayes | 2023-12-04 | 2023-12-13 | Complete
LSRMS/CW/119 | Berryfields Road | 2024-01-03 | 2024-01-15 | Complete
LSRMS/CW/118 | Melvina Road | 2024-01-15 | 2024-01-24 | Complete
BHMMS-0551 | Oxhill Road (FW) | 2024-01-22 | 2024-01-31 | Complete
BHMMS-0642-1 | Genners Lane | 2024-01-29 | 2024-01-29 | Complete
LSRMS/CW/121 | Reddings Road | 2024-01-30 | 2024-01-31 | Complete
BHMMS-870 | Chimes Close | 2024-02-29 | 2024-02-29 | Complete
LSRMS/CW/123 | Overbury Road | 2024-04-12 | 2024-04-12 | Live
BHMMS-0642 | Grove Road | 2024-04-13 | 2024-04-14 | Programmed
BHMMS-0642-2 | Raddlebarn Road | TBC | TBC | Programmed
BHMMS-0530B | Warstock Lane, Billesley | TBC | TBC | Programmed