## Sheet1
Scheme Ref no | Road | District | Ward | Start | Finish | Comments
LSRMS/CW/119 | Berryfields Road | Sutton Walmley & Minworth | Sutton Coldfield | 2024-01-03 | 2024-01-15 | Complete
LSRMS/CW/118 | Melvina Road | Nechells | Ladywood | 2024-01-15 | 2024-01-24 | Complete | Key
BHMMS-0551 | Oxhill Road (FW) | Handsworth Wood | Perry Barr | 2024-01-22 | 2024-01-31 | Complete | Night Works
BHMMS-0642-1 | Genners Lane | Bartley Green | Edgbaston | 2024-01-29 | 2024-01-29 | Complete | Deferred
LSRMS/CW/121 | Reddings Road | Moseley | Hall Green | 2024-01-30 | 2024-01-31 | Complete
BHMMS-870 | Chimes Close | Yardley | Sheldon | 2024-02-29 | 2024-02-29 | Complete
LSRMS/CW/123 | Overbury Road | Bourneville Cotteridge | Selly Oak | 2024-04-12 | 2024-04-12 | Complete
BHMMS-0642 | Grove Road | Brandwood & Kings Heath | Selly Oak | 2024-04-13 | 2024-04-14 | Complete
BHMMS-0530AA | Warstock Lane | Billesley | Selly Oak | 2024-07-08 | 2024-07-16 | Complete
BHMMS-1209 | Hartfield Crescent | Acocks Green | Billesley | 2024-11-11 | 2024-11-14 | Complete
BHMMS-1215 | William Henry Street | Ladywood | Nechells | 2024-11-16 | 2024-11-17 | Complete
BHMMS-0642-2 | Raddlebarn Road | Bounrbook and Selly Oak | Selly Oak | 2025-01-15 | 2025-01-30 | Complete
BHMMS-0934 | Salisbury Road | Edgebaston | Hall Green and Moseley | 2025-02-03 | 2025-02-05 | Complete
BHMMS-1665 | Sidcup Road | Kingstanding | Oscott | 2025-07-07 | 2025-07-17 | To Be Programmed
BC-004 | Rotton Park Road | North Edgbaston | Edgbaston | TBC | TBC | To Be Programmed
BC-005 | Oscott School Lane | Oscott | Erdington | TBC | TBC | To Be Programmed
BC-006 | Lower Parade | Sutton Trinity | Sutton Coldfield | TBC | TBC | To Be Programmed
BC-002 | Clarence Road | Sutton Mere Green | Sutton Coldfield | TBC | TBC | To Be Programmed
BC-001 | Green Road | Yardley | Hall Green North | TBC | TBC | To Be Programmed
TBC | Cole Bank Road | Hall Green | Hall Green South | TBC | TBC | To Be Programmed
BHMMS-0530A | Warstock Lane |  |  |  |  | Deferred