## Annex 1
LOCAL GROWTH FUND - SUMMARY PROGRAMME (2015/16 - 2021) - 13 October 2015 ANNEX 1
Ref No | Project Title | Project Sponsor | Designated Programme Manager | RAG | Total Project Cost £m | LGF Allocation £m | Proposed Allocation 2015/16 £m | Original Request for Prep Costs 2015/16 £m | Capital Spend 2015/16 £m | Likely Allocation 2015/16 £m | Capital Spend 2016/17 £m | Capital Spend 2017/18 £m | Capital Spend 2018/19 £m | Capital Spend 2019/20 £m | Capital Spend 2020/21 £m | Notes
LESS THAN <£2.5M
6 | Journey Time Reliability Improvements to Growth Areas | BCC | LE | C | 2.69 | 2.416 | 0.616 | 0 | 0.616 | 0.616 | 0.45 | 0.45 | 0.45 | 0.45 | 0 | Approved. SLA being developed and on site September 2015..
8 | Battery Way Extension, Tyseley | BCC | LE | C | 2.72 | 2.45 | 0.2 | 0.2 | 0 | 0.2 | 2.25 | 0 | 0 | 0 | 0 | An Additional £1.2m was approved on the 2/9/2015 by the Growth Team and the Project has been recommended for approval by the ITE at the increased £2.45m.
18 | Lode Lane | SMBC | LE | C | 4.665 | 1.79 | 1.79 | 0 | 1.79 | 1.79 | 0 | 0 | 0 | 0 | 0 | Approved - Noted by Supervisory Board 23/7/2015.
19 | Mid-Cannock interchange | Cannock DC | RS |  | 14.3 | 1.296 | 0.6 | 0 | 0.6 | 0.6 | 0.699 | 0 | 0 | 0 | 0 | Approved - funding agreement on hold. We have been informed (31/7/2015) that Pentalver was unsuccessful in their bid for European Funding (CEF) and will now be seeking options to progress the project with their shareholders - a decision is expected end of October 2015 when the Growth Team will be asked to agree to the withdrawal of the funding if a positive outcome hasn't been agreed by the shareholders.
21 | East Staffs Growth and Regen Prog | ESDC | LE | C | 5.7 | 1.5 | 1.5 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement being developed.
24 | Food Technology Hub | University College | LE | C | 0.75 | 0.34 | 0.34 | 0 | 0.34 | 0.34 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement being developed. Noted by Supervisory Board 23/7/2015.
25 | Universities@IBC | Innovation Birmingham | LE | C | 14 | 2.49 | 0.71679 | 0 | 0.71679 | 0.71679 | 1.7772 | 0 | 0 | 0 | 0 | Approved - Funding Agreement signed off 6th August 2015. Noted at Supervisory Board 23/7/2015.
28 | Kidderminster Railway Station | Worcestershire CC | RS |  | 4.8 | 1.8 | 0.18 | 0.18 | 0 | 0.18 | 0.62 | 1 | 0 | 0 | 0 | Full Business Case expected December 2016 therefore spend in 2017/18. It is anticipated that the total cost of the project will be circa £4.8m and that WCC may be involved in its development. The project will be monitored and amended following receipt of the FBC.
29 | Motor Vehicle Training Centre | South & City College | LE | C | 0.6 | 0.26 | 0.26 | 0 | 0.26 | 0.26 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement to be signed off October 2015. Noted by Supervisory Board 23/7/2015.
30 | HS2 Construction Centre | [14 empty] | Withdrawn by the Project Sponsor due to funding challenges
31 | Aviation Engineering Training Centre | Solihull College | LE | C | 2.17 | 0.89 | 0.89 | 0 | 0.89 | 0.89 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement signed off plus Deed of Variation for an additional £56k. Noted by Supervisory Board 23/7/2015.
32 | Engineering Centre for Manufacturing Support | South & City College | LE | C | 0.45 | 0.207 | 0.207 | 0 | 0.207 | 0.207 | 0 | 0 | 0 | 0 | 0 | Approved - Awaiting for the project sponsor to sign off funding agreement. Noted by Supervisory Board 23/7/2015.
33 | Advanced Manufacturing Hub | BCC | LE | C | 10 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | ITE recommended approval.
35 | Kingswood Lakeside Access Phase 1 | Staffordshire CC | RS | C | 8 | 0.8 | 0.8 | 0 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | Additional £700,000 agreed in principle by the Growth Team on the 2/9/2015.
42 | Advanced Life Science Facilities | Solihull College | RS |  | TBC | 0.62 | 0 | 0 | 0 | 0 | 0.62 | 0 | 0 | 0 | 0 | BC will not be submitted until 2016/17 as originally planned
43 | Meeting the Skills Needs of Local Businesses | South & City College | LE | C | 0.3 | 0.13 | 0.13 | 0 | 0.13 | 0.13 | 0 | 0 | 0 | 0 | 0 | Approved - awaiting funding agreement to be signed off by Project Sponsor. Noted by Supervisory Board 23/7/2015.
| WMG Academy for Young Engineers (Future Skills Fund) | WMG University Technical College | LE |  | 2.2 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed.
| Summer Row Skills Enhancement project (Future Skills Fund) | University College Birmingham | RS |  | 2.8 | 1.067 | 0.762 | 0 | 0.762 | 0.762 | 0.305 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed.
| Engineering Centre of Excellence - Redditch (Future Skills Fund) | MGTS | LE |  | 1.58 | 0.35 | 0.35 | 0 | 0.35 | 0.35 | 0 | 0 | 0 | 0 | 0 | Draft Business Case received prior to submission to SFA for an independent technical evaluation.
| EEF (Future Skills Fund) | EEF | RS |  |  | 0.3 | 0.3 | 0 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | Outline application being developed and allocation ring fenced.
| Lode Lane Phase 2 | SMBC | RS |  |  | 1.4 | 1.4 | 0 | 1.4 | 0.24 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed but three local councillors as well as the local MP (Julian Knight) now object to the scheme on the back of the traffic management trial. Business case still being developed but revised spend profile predicted.
| AMH Phase 1 | BCC | LE |  | 2.45 | 2.45 | 2.45 | 0 | 2.45 | 2.45 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case recommended by the ITE but job outputs to be confirmed.
| Moss Road Estate Development | CCDC | RS |  |  | 0.8 | 0.8 | 0 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed.
| Friarsgate | Lichfield DC | RS |  |  | 2.4 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed.
| Kingswood Lakeside Access Phase 2 | Staffordshire CC | RS |  | 8 | 0.7 | 0.7 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | Additional £700,000 agreed in principle by the Growth Team on the 2/9/2015.
| Chester Road | BCC | LE |  | 12.4 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed.
| Sub Total |  |  |  | 100.575 | 30.556 | 17.9918 | 0.38 | 17.6118 | 16.8318 | 10.2212 | 1.45 | 0.45 | 0.45 | 0
BETWEEN £2.5M AND £10M
1 | Hagley Road SPRINT | Centro | RS |  | 12.2 | 8.1 | 2 | 0.46 | 1.54 | 1.396 | 5.86 | 0.235 | 0 | 0 | 0 | Concern regarding spend in 2015/16 due to timescale to confirm DfT derogation which is still outstanding. Proposal to split this into two workstreams for bus and infrastructure and revise spend profile accordingly however, infrastructure is also a concern therefore, should the preparatory fees be approved if there is uncertainty regarding the projects delivery.
2 | Ashted Circus, Birm'ham Ring Road | BCC | RS |  | 6.673 | 4.07 | 0.37 | 0.05 | 0.32 | 0.37 | 3.7 | 0 | 0 | 0 | 0 | BC slipped to October due to some remodelling work.
3 | Longbridge Connectivity Scheme | BCC | RS | C | 8.09 | 4.87 | 1.5 | 0.4 | 1.1 | 1.51 | 3.36 | 0 | 0 | 0 | 0 | Growth Team approved 2/9/2015 and noted by Supervisory Board in September 2015. SLA being developed but re-profiling of expenditure to be confirmed as the anticipated £1.5m in 2015/16 has reduced to £0.6m. A separate business case was invited by the Growth Team to be developed for the Park and Ride project for £1.2m. Application for preparatory fees awaiting Project Lead sign off and approval
| Longbridge Connectivity - MSCP | Centro | RS |  |  | 1.2 | 1.2 | 0.25 | 0.95 | 0.2 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed.
4 | Midland Metro Birmingham Eastside Extension | Centro | RS | C | 102.6 | 5.5 | 2.524 | 2.524 | 0 | 2.524 | 2.976 | 0 | 0 | 0 | 0 | Approved - Preparatory fees approved and noted by the Supervisory Board. Funding agreement for £5.5m signed off and claim submitted.
5 | Snow Hill Station Phase 1 & 2 | BCC | RS |  | 9.99 | 4.66 | 0.326 | 0.326 | 0 | 0.33 | 2.2 | 2.127 | 0 | 0 | 0 | BC has slipped and now expected Autumn/Winter 2015. Phase 1 - amended from Green to Amber and Phase 2 Red. Snow Hill Board to agree way forward at their October meeting.
7 | Birmingham Cycle Revolution Phase 2 | BCC | RS | C | 8 | 5.995 | 1 | 0.725 | 0.27 | 1.2 | 1 | 2 | 1 | 1 | 0 | Growth Team approved 2/9/2015 and noted by the Supervisory Board September 2015. SLA awaiting sign off. Application for preparatory fees have been claimed.
9 | One Station | BCC | RS |  | 5 | 3.5 | 0 | 0 | 0 | 0 | 1 | 2.3 | 0 | 0 | 0 | Business Case to be submitted early Autumn - AECOM have now been appointed. Some reservation as to whether capital works will start this year, hence reduced to zero.. Andrew Cleaves wants to review before sign off.
10 | University Station Interchange | Centro | RS |  | 3.09 | 2.59 | 0.466 | 0.466 | 0 | 0.47 | 2.12 | 0 | 0 | 0 | 0 | Preparatory fees application submitted 3/8/2015 and approved at 18% due to increased design costs. FBC will be submitted February 2016.
11 | South Kidderminster Enterprise Park – Hoobrook Link Road | Worcs CC | LE |  | 16.3 | 4.8 | 4.8 | 0 | 4.8 | 4.8 | 0 | 0 | 0 | 0 | 0 | Increased allocation agreed at the 2/9/2015 Growth Team. Awaiting updated information on additional benefits and confirmation that key projects will continue to be delivered.
12 | Iron Lane, Birmingham | BCC | RS |  | 9.66 | 5 | 0.35 | 0.35 | 0 | 0.35 | 3.24 | 1.414 | 0 | 0 | 0 | Business case slipped to 31 October 2015 as further modelling is now required. Construction timetable may slip from Spring 2016 (subject to 3rd party land being secured) to October 2016 if a CPO without inquiry is required.
13 | Metro Ext to Centenary Square | Centro/BCC | LE | C | 42.4 | 8 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement signed off for Centro. DoV completed for additional £3.1m
14 | Sustainable Urban Extension - Minworth | BCC | LE |  | 11.11 | 2.288 | 0.35 | 0.22 | 0.13 | 0.35 | 1.938 | 0 | 0 | 0 | 0 | BC received and passed to HCA for ITE assessment.
| Sustainable Urban Extension - Peddimore | BCC | RS |  |  | 2.71 | 0 | 0 | 0 | 0 | 0.23 | 2.48 | 0 | 0 | 0 | BC expected October 2015.
15 | Making the Connections | BCC | RS |  | 8 | 6.8 | 0.476 | 0.476 | 0 | 0.48 | 0.6 | 5.72 | 0 | 0 | 0 | BC expected Autumn 2015 - AECOM have been commissioned to complete the business case. Preparatory fees application has not yet been submitted.
16 | Selly Oak New Road Phase 1b | BCC | RS |  | 6.13 | 3.63 | 0.2 | 0.2 | 0 | 0.11 | 0 | 1.49 | 1.643 | 0.3 | 0 | BC slipped as further modelling work required. 2015/16 development fees required. Conditional offer letter provided.
17 | Unblocking small housing sites Phase 1 and 2 | BCC | LE |  | 9 | 9 | 0.3 | 0 | 0.3 | 0.3 | 2.8875 | 2.91 | 2.9 | 0 | 0 | Growth Team approved 2/9/2015 and noted by the Supervisory Board September 2015. Draft SLA being developed.
20 | A34 corridor - Perry Barr | BCC | RS | C | 6.1 | 3.5 | 0.8 | 0.1 | 0.7 | 0.8 | 2.5 | 0.2 | 0 | 0 | 0 | Approved - subway infill and land assembly. Application for preparatory fees has been agreed. SLA being developed.
22 | Future Skills Capital |  | LE/RS | [12 empty] | Funds allocated to skills capital projects.
23 | Wholesale Markets | BCC | LE |  | 44.37 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Business case submitted by AMION and recommended for approval by ITE (awaiting recommendation). Start on site November and spend this year.
26 | Life Sciences Centre | Bourneville College | RS |  | 4.9 | 2.4 | 0 | 0 | 0 | 0 | 1 | 1.4 | 0 | 0 | 0 | Concern still continues regarding the delivery of the project - it is anticipated that approval from the Growth Team will be sought in November to withdraw the project.
34 | Life Sciences Campus | BCC | RS |  | 171 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Green amended to Green/Amber - spend now needed for infrastructure costs in 2016/17. Business case should have been submitted in April but slipped to Autumn 2015.
| Midland Metro Catenary | Centro | RS |  |  | 3.2 | 3.2 | 0 | 3.2 | 3.2 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed.
| National College for High Speed Rail | BCC | RS |  |  | 6 | 0.6 | 0.6 | 0 | 0.6 | 3.264 | 2.136 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/2015 - business case being developed. Development fee application submitted
| Sub Total |  |  |  | 484.613 | 105.813 | 36.462 | 7.147 | 29.31 | 29.99 | 37.8755 | 24.412 | 5.543 | 1.3 | 0
GREATER THAN £10M
27 | Centre for Advanced Technologies | Birmingham Met College | [13 empty] | Letter received from BMET dated 19th May 2015 declining the offer of the LGF due to considerable budget cuts and the colleges need to rationalise the sites as well as reviewing planned capital investment.
| Sub Total |  |  |  | 0 | 0
| TOTAL |  |  |  | 585.188 | 136.369 | 54.4538 | 7.527 | 46.9218 | 46.8218 | 48.0967 | 25.862 | 5.993 | 1.75 | 0
| LGF TARGET SPEND |  |  |  |  | 131.855 | 47.3135 |  |  | 47.3135 | 49.1755 | 13.0732 | 9.0734 | 7.4827 | 5.7367
| VARIATION | [5 empty] | 7.1403 |  |  | -0.4917 | -1.0788 | 12.7888 | -3.0804 | -5.7327 | -5.7367
| % | [5 empty] | 115.1% |  |  | 98.96% | 97.81% | 197.8% | 66.05% | 23.39% | 0%
PORTFOLIO SCHEMES
37 | Tame Valley Viaduct - Phase 3 |  | RS |  | 82.01 | 72.01 | [9 empty] | DfT offered £2.2m for development fees under S31 grant to be spent in 2015/16.
38 | A457 Dudley Road | BCC | RS |  | 29.5 | 22.41 | 0.5 | 0.5 |  | 0.5
39 | A45 Rapid Transit City-Airport | Centro | RS |  | 50 | 35 | 0.2 | 0.2 |  | 0.2
40 | Metro Ext to Edgbaston | Centro | RS |  | 67.5 | 59.8 | 1.5 | 1.5 |  | 1.5
41 | Midland Metro Eastside Extn | Centro | RS |  |  | 35
| Sub Total |  |  |  | 229.01 | 224.22 | 2.2 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0
| Growth Deal Total Allocation |  |  |  |  | 360.589
RAG Code:
| FBC approved and now in contract |  |  | C
| FBC approved and contract being developed or ITE recommended approval but subject to Growth Team approval. |  |  | C
FBC being developed
Potential delay identified in project delivering within timeframe or budget.
New FBC being develop or FBC slipping and concerns raised regarding delivery and spend in 2015/16. Actions within the risk register.
FBC slipping and concerns raised regarding delivery and spend. Actions within the risk register.
FBC will not deliver. Actions within the risk register.
#