## Annex 1
LOCAL GROWTH FUND - SUMMARY PROGRAMME (2015/16 - 2021) - 19 November 2015 ANNEX 1
Ref No | Project Title | Project Sponsor | Designated Programme Manager | RAG | Total Project Cost £m | LGF Allocation £m | Proposed Allocation 2015/16 £m | Original Request for Prep Costs 2015/16 £m | Capital Spend 2015/16 £m | Likely Allocation 2015/16 £m | Capital Spend 2016/17 £m | Capital Spend 2017/18 £m | Capital Spend 2018/19 £m | Capital Spend 2019/20 £m | Capital Spend 2020/21 £m | Notes
LESS THAN <£2.5M
6 | Journey Time Reliability Improvements to Growth Areas | BCC | LE | C | 1.38 | 1.111 | 0.21099 | 0 | 0.21099 | 0.21099 | 0.225 | 0.225 | 0.225 | 0.225 | 0 | Approved. SLA expected to be signed off November 2015.
| Journey Time Reliability Improvements to Growth Areas | SMBC | LE | C | 1.47 | 1.3055 | 0.40547 | 0 | 0.40547 | 0.40547 | 0.225 | 0.225 | 0.225 | 0.225 | 0 | Approved and in contract. Started on site September 2015.
8 | Battery Way Extension, Tyseley | BCC | LE | C | 2.72 | 2.45 | 0.2 | 0.2 | 0 | 0.13 | 0.5 | 1.82 | 0 | 0 | 0 | An additional £1.2m was approved on the 2/9/15 by the Growth Team and the Project has been recommended for approval by the ITE at the increased £2.45m. SLA due to be signed off November 2015. Start date delayed as CPO to be factored into the programme timescale therefore start date slipped from June 2016 to May 2017.
18 | Lode Lane | SMBC | LE | C | 4.665 | 1.79 | 1.79 | 0 | 1.79 | 1.79 | 0 | 0 | 0 | 0 | 0 | Approved - Noted by Supervisory Board 23/7/2015. On site 2 November 2015.
19 | Mid-Cannock interchange | Cannock DC | RS |  | 14.3 | 1.299 | 0.6 | 0 | 0.6 | 0.6 | 0.699 | 0 | 0 | 0 | 0 | Approved - funding agreement on hold. Project has been noted on the Sanctions Paper report to Growth Team on the 27 November 2015 where more information is available.
21 | East Staffs Growth and Regen Prog | ESDC | LE | C | 5.7 | 1.5 | 1.5 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement expected to be signed off November 2015
24 | Food Technology Hub | University College | LE | C | 0.75 | 0.34 | 0.34 | 0 | 0.34 | 0.34 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement expected to be signed off November 2015. Noted by Supervisory Board 23/7/15.
25 | Universities@IBC | Innovation Birmingham | LE | C | 14 | 2.4937 | 0.72 | 0 | 0.72 | 0.57155 | 1.9221 | 0 | 0 | 0 | 0 | Approved - Funding Agreement signed off 6 August 2015. Noted at Supervisory Board 23/7/2015. Due to delayed planning application start on site delayed to Jan 16.
28 | Kidderminster Railway Station | Worcestershire CC | RS |  | 4.3 | 1.8 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | Full Business Case expected July 2016. It is anticipated that WCC may be involved in its development as they are contributing £2.5m match funding. The project will be monitored and amended following receipt of the FBC.
29 | Motor Vehicle Training Centre | South & City College | LE | C | 0.6 | 0.26 | 0.26 | 0 | 0.26 | 0.26 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement to be signed off November 2015. Noted by Supervisory Board 23/7/15.
31 | Aviation Engineering Training Centre | Solihull College | LE | C | 2.17 | 0.89 | 0.89 | 0 | 0.89 | 0.89 | 0 | 0 | 0 | 0 | 0 | Approved - Funding Agreement signed off plus Deed of Variation for an additional £56k. Noted by Supervisory Board 23/7/2015. £347k claimed to date
32 | Engineering Centre for Manufacturing Support | South & City College | LE | C | 0.467 | 0.21 | 0.207 | 0 | 0.207 | 0.21 | 0 | 0 | 0 | 0 | 0 | Approved - Awaiting for the project sponsor to sign off funding agreement. Noted by Supervisory Board 23/7/15.
33 | AMH Phase A - (JB Foods & Rylands Garage) | BCC | LE | C | 10 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | FBC has been received and recommended for approval by the ITE. The project has been combined with the acquisition for the AMH Phase B (Concentric Controls) to create a £4.45m application that will create 641 direct jobs and 1,041 indirect jobs on the site and within the supply chain.
35 | Kingswood Lakeside Access Phase 1 | Staffordshire CC | RS | C | 8 | 0.8 | 0.8 | 0 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | Approved - funding agreement due to be signed off November 2015.
42 | Advanced Life Science Facilities | Solihull College | RS |  |  | 0.62 | 0 | 0 | 0 | 0 | 0.62 | 0 | 0 | 0 | 0 | BC will be submitted between Jan to March 2016. Potential to revise this proposal and increase the Aviation College to deliver greater benefits.
43 | Meeting the Skills Needs of Local Businesses | South & City College | LE | C | 0.3 | 0.13 | 0.13 | 0 | 0.13 | 0.13 | 0 | 0 | 0 | 0 | 0 | Approved - awaiting funding agreement to be signed off by Project Sponsor. Noted by Supervisory Board 23/7/15.
| WMG Academy for Young Engineers (Future Skills Fund) | WMG University Technical College | LE | C | 2.2 | 1.1 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | Growth Team agreed on the 2/9/15 for a business case to be developed. Evaluated and passed to PDD for approval. Legal instructed to prepare funding agreement.
| Summer Row Skills Enhancement project (Future Skills Fund) | University College Birmingham | RS |  | 2.8 | 1.067 | 0.762 | 0 | 0.762 | 0.762 | 0.305 | 0 | 0 | 0 | 0 | Growth Team agreed on the 2/9/15 for a business case to be developed. Outline application received and Programme Manager to work with the college to develop the business case.
| Engineering Centre of Excellence - Redditch (Future Skills Fund) | MGTS | LE |  | 1.58 | 0.35 | 0.35 | 0 | 0.35 | 0.35 | 0 | 0 | 0 | 0 | 0 | Business Case received and passed to SFA for independent ITE on 16/10/15.
| Lode Lane Phase 2 | SMBC | RS |  | 3.47 | 1.686 | 1.4 | 0 | 1.4 | 0.4 | 1.286 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/15 to develop a business case which will be submitted 26 November 2015. Expected to start on site 25 January 2016.
| AMH Phase B (Concentric Controls) | BCC | LE |  | 2.45 | 2.45 | 2.45 | 0 | 2.45 | 2.45 | 0 | 0 | 0 | 0 | 0 | FBC has been received and recommended for approval by the ITE. The project has been combined with the acquisition for the AMH Phase A (JB Food and Ryland Garage reclamation) to create a £4.45m application that will create 641 direct jobs and 1,041 indirect jobs on the site and within the supply chain.
| Moss Road Estate Development | CCDC | RS |  |  | 0.8 | 0.8 | 0 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/15 for a business case to be developed.
| Friarsgate | Lichfield DC | RS |  | 51.596 | 2.4 | 0 | 0 | 0 | 0 | 1.5 | 0.9 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/15 for a business case to be developed. Received draft for comment 21/10/15 but aiming for approval December 2015.
| Kingswood Lakeside Access Phase 2 | Staffordshire CC | RS |  | 8 | 0.7 | 0.7 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | Growth Team on the 2/9/15 agreed in principle an additional £700,000 subject to additional benefits being identified.
| Chester Road | BCC | LE |  | 12.4 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/15 for a business case to be developed which was received on the 16 November 2015.
| Sub Total |  |  |  | 155.318 | 30.5522 | 17.5155 | 0.2 | 17.3155 | 16.3 | 10.1821 | 3.17 | 0.45 | 0.45 | 0
BETWEEN £2.5M AND £10M
1 | Hagley Road SPRINT | Centro | RS |  | 12.2 | 8.1 | 2 | 0.46 | 1.54 | 1.396 | 6.469 | 0.235 | 0 | 0 | 0 | DfT derogation is still outstanding. DfT are awaiting information from the Belgium Ministry of Transport regarding Axle loadings. The DfT have advised Centro that the change in legislation required could be included in the December Statement of New regulation but more than likely July 2016 due to other priorities. Centro have sent DfT a note for Ministers, highlighting the continued importance of this derogation decision for the West Midlands, and highlighting the potential reputational risk on delivery for all parties. The FBC is expected to be received and signed off by December 2015.
2 | Ashted Circus, Birm'ham Ring Road | BCC | RS |  | 6.673 | 4.07 | 0.37 | 0.05 | 0.32 | 0.37 | 3.7 | 0 | 0 | 0 | 0 | FBC slipped from October to November 2015 as the VISSIM remodelling benefits have to be reviewed. Expected start on site July 2016. It is anticipated that an additional £850k will be requested when the FBC is submitted.
3 | Longbridge Connectivity Scheme | BCC | RS | C | 6.83 | 4.86 | 1.5 | 0.4 | 1.1 | 0.6 | 4.26 | 0 | 0 | 0 | 0 | Growth Team approved 2/9/2015 and noted by Supervisory Board in September 2015. SLA being developed but re-profiling of expenditure to be confirmed as the anticipated £1.5m in 2015/16 has reduced to £0.6m. A separate business case was invited by the Growth Team to be developed for the Park and Ride project for £1.2m. Application for preparatory fees awaiting Project Lead sign off and approval
| Longbridge Connectivity - MSCP | Centro | RS |  | 1.97 | 1.2 | 1.2 | 0.25 | 0.95 | 0.7 | 0.5 | 0 | 0 | 0 | 0 | A separate business case was invited by the Growth Team to be developed for the Park and Ride project for £1.2m. Full business case has been received and submitted to the ITE. A report for Longbridge Connectivity will include the MSCP which is expected to go to the 8th December Cabinet.
4 | Midland Metro Birmingham Eastside Extension | Centro | RS | C | 102.6 | 5.4961 | 2.5239 | 2.5239 | 0 | 2.52 | 2.9761 | 0 | 0 | 0 | 0 | Approved. Preparatory fees approved and noted by the Supervisory Board. Funding agreement for £5.5m signed off and claim submitted for 2015/16.
5 | Snow Hill Station Phase 1 & 2 | BCC | RS |  | 9.99 | 4.6 | 0.326 | 0.326 | 0 | 0 | 1.3 | 2.8 | 0.5 | 0 | 0 | Project has been noted on the Sanctions Paper report to Growth Team on the 27 November 2015. Concerns regarding Phase 1 - Tranche 1 due to Standard Life support needed as a landowner. Seeking to resolve difficulties by end of November 2015.
7 | Birmingham Cycle Revolution Phase 2 | BCC | RS | C | 8 | 6 | 1 | 0.725 | 0.27 | 1.2 | 0.8 | 2 | 1 | 1 | 0 | Growth Team approved on 2/9/15 and noted by Supervisory Board in Sept 2015. SLA signed off and preparatory fees claimed.
9 | One Station | BCC | RS |  | 5 | 3.3 | 0 | 0 | 0 | 0 | 1 | 2.3 | 0 | 0 | 0 | Project has been noted on the Sanctions Paper report to Growth Team on the 27 November 2015. Business Case slipped from early Autumn submission to February 2016. AECOM have now been appointed to expedite.
10 | University Station Interchange | Centro | RS |  | 3.09 | 2.59 | 0.466 | 0.466 | 0 | 0.47 | 2.12 | 0 | 0 | 0 | 0 | Development Design to GRIP 4 now January 2016. Therefore FBC has slipped from February to March 2016. Preparatory fees application submitted 3/8/15 and approved at 18% due to increased design costs.
11 | South Kidderminster Enterprise Park – Hoobrook Link Road | Worcs CC | LE |  | 16.254 | 4.8 | 4.8 | 0 | 4.8 | 4.8 | 0 | 0 | 0 | 0 | 0 | Increased allocation agreed at the 2/9/15 by Growth Team. Awaiting updated information on additional benefits/revised business case based on increased allocation for ITE. Project Sponsor has been asked to provide the information as matter of urgency.
12 | Iron Lane, Birmingham | BCC | RS |  | 9.66 | 5.004 | 0.35 | 0.35 | 0 | 0.35 | 3.24 | 1.414 | 0 | 0 | 0 | Project has been noted on the Sanctions Paper report to Growth Team on the 27 November 2015 as it is now seeking an additional £2m (not included in this spend profile). The FBC has been received and will be evaluated w/c 23/11/15.
13 | Metro Ext to Centenary Square | Centro | LE | C | 42.4 | 7.55 | 7.55 | 0 | 7.55 | 7.55 | 0 | 0 | 0 | 0 | 0 | Approved. Funding Agreement signed off for Centro. Revised Deed of Variation completed for £2.7m and an SLA has been developed for BCC complimentary highway works for £4.5m for LGF.
| Metro Ext to Centenary Square - Complementary Highway Works | BCC | LE | C | 0.45 | 0.45 | 0.45 | 0 | 0.45 | 0.45 | 0 | 0 | 0 | 0 | 0 | Approved. Funding Agreement being developed for complimentary highway works which has been drawn down from the LGF.
14 | Sustainable Urban Extension - Minworth | BCC | LE | C | 11.11 | 2.358 | 0.35 | 0.22 | 0.13 | 0.42 | 1.938 | 0 | 0 | 0 | 0 | BC received and passed to HCA for ITE assessment.
| Sustainable Urban Extension - Peddimore | BCC | RS |  |  | 2.64 | 0 | 0 | 0 | 0 | 0.32 | 2.32 | 0 | 0 | 0 | BC expected October 2016.
15 | Making the Connections | BCC | RS |  | 8 | 6.8 | 0.476 | 0.476 | 0 | 0.48 | 0.6 | 5.72 | 0 | 0 | 0 | Project has been noted on the Sanctions Paper report to Growth Team on the 27 November 2015. BC expected Autumn 2015. AECOM have been commissioned to complete the business case. Preparatory fees application outstanding.
16 | Selly Oak New Road Phase 1b | BCC | RS |  | 6.13 | 3.633 | 0.2 | 0.2 | 0 | 0.11 | 0.11 | 1.49 | 1.623 | 0.3 | 0 | BC expected 30 November 2015. Previously slipped due to further modelling work required. 2015/16 development fees required. Conditional offer letter provided.
17 | Unblocking small housing sites Phase 1 and 2 | BCC | LE | C | 9 | 8.9975 | 0.3 | 0 | 0.3 | 0.3 | 2.8875 | 2.91 | 2.9 | 0 | 0 | Growth Team approved 2/9/15 and noted by the Supervisory Board September 2015. SLA awaiting sign off by the Project Sponsor.
20 | A34 corridor-Perry Barr Phase 1 | BCC | RS | C | 6.1 | 3.5 | 0.8 | 0.1 | 0.7 | 0.8 | 1.1 | 1.6 | 0 | 0 | 0 | Approved, subway infill and land assembly business case for Phase 1. Application for preparatory fees has been agreed. SLA being developed.
23 | Wholesale Markets | BCC | LE |  | 44.37 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Business case submitted by AMION and recommended for approval by ITE subject to minor amendments. BCC to provide a state aid letter of compliance from BCC legal. BCC have now got more than 60% of tenants signed so over the hurdle for BCC’s ‘minimum case’.
26 | Life Sciences Centre | Bourneville College | RS |  | 4.9 | 2.4 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | Project has been noted on the Sanctions Paper report to Growth Team on the 27 November 2015. Concern still continues regarding the delivery due to no viable match funding being offered.
34 | Life Sciences Campus | BCC | RS |  | 171 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | FBC expected December 2015.
| Midland Metro Catenary | Centro | RS |  |  | 3.2 | 3.2 | 0 | 3.2 | 3.2 | 0 | 0 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/15 - business case being developed.
| National College for High Speed Rail | BCC | RS |  |  | 6 | 0.6 | 0.6 | 0 | 0.6 | 3.264 | 2.136 | 0 | 0 | 0 | Agreed by the Growth Team 2/9/15 - business case being developed. Development fee application submitted
| Sub Total |  |  |  | 485.727 | 105.5486 | 36.4619 | 7.1469 | 29.31 | 34.316 | 38.9846 | 24.925 | 6.023 | 1.3 | 0
Capitalised Costs
| Capitalsied costs | GBS LEP |  |  |  | 1.9 | 0.3 |  | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 |  | Withdrawn by the Project Sponsor due to funding challenges
| TOTAL |  |  |  | 641.045 | 138.0008 | 54.2773 | 7.3469 | 46.9255 | 50.916 | 49.5668 | 28.495 | 6.873 | 2.15 | 0
| LGF TARGET SPEND | [5 empty] | 47.3135 |  |  | 47.3135 | 49.1755 | 13.0732 | 9.0734 | 7.4827 | 5.7367
| VARIATION | [5 empty] | 6.9638 |  |  | 3.6025 | 0.3913 | 15.4218 | -2.2004 | -5.3327 | -5.7367
| % | [5 empty] | 114.7% |  |  | 107.6% | 100.8% | 218% | 75.75% | 28.73% | 0%
PORTFOLIO SCHEMES
37 | Tame Valley Viaduct - Phase 3 |  | RS |  | 82.01 | 72.01 |  |  |  | 0
38 | A457 Dudley Road | BCC | RS |  | 29.5 | 22.41 | 0.5 | 0.5 |  | 0.5 | 0.5 | 2 | 6 | 13.411 | 0 | DfT offered Section 31 grant to cover development fees. Submission of business case to DfT Autumn 2016 and start on site expected March 2019. Spend profile from 2020/21 required.
39 | A45 Rapid Transit City-Airport | Centro | RS |  | 50 | 35 | 0.2 | 0.2 |  | 0.2 | [5 empty] | DfT offered Section 31 grant to cover development fees. Acceptance of Section 31 to be requested to include outputs. FBC expected to be completed March 2017 and projected expected to start 2018/19.
40 | Metro Ext to Edgbaston | Centro | RS |  | 67.5 | 59.8 | 1.5 | 1.5 |  | 1.5 | [5 empty] | DfT offered Section 31 grant to cover development fees. Acceptance of Section 31 to be requested to include outputs. Completion of financial business case expected 19/1/2016. Start on site 1/3/2019 and completion 15/2/21.
41 | Midland Metro Eastside Extn | Centro | RS |  |  | 35 |  |  |  | 0
| Sub Total |  |  |  | 229.01 | 224.22 | 2.2 | 2.2 | 0 | 2.2 | 0.5 | 2 | 6 | 13.411 | 0
Removed or Withdrawn Projects
22 | Future Skills Capital |  |  |  |  | 0 | [9 empty] | Funds allocated to skills capital projects.
27 | Centre for Advanced Technologies | Birmingham Met College |  |  |  | 0 | [9 empty] | Letter received from BMET dated 19th May 2015 declining the offer of the LGF due to considerable budget cuts and the colleges need to rationalise the sites as well as reviewing planned capital investment.
30 | HS2 Construction Centre | South & City College |  |  |  | 0 | [9 empty] | Withdrawn by the Project Sponsor due to funding challenges
| LGF Total Grant Allocation |  |  |  |  | 357.05
| LGF Project Allocation |  |  |  |  | 362.2208
| Variation |  |  |  |  | 5.1708
RAG Code:
| FBC approved and now in contract |  |  | C
| FBC approved and contract being developed or ITE recommended approval but subject to Growth Team approval. |  |  | C
FBC being developed
Potential delay identified in project delivering within timeframe or budget.
New FBC being develop or FBC slipping and concerns raised regarding delivery and spend in 2015/16. Actions within the risk register.
FBC slipping and concerns raised regarding delivery and spend. Actions within the risk register.
FBC will not deliver. Actions within the risk register.
#