## Carriageways IIP
Carriageways IIP Programme
[9 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01
[9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
Task ID | Task Name | Ward | Scheme Extents | Treatment | Design Option | START | END | DAYS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1100085A | Dreghorn Road | Bromford & Hodge Hill | Dreghorn Road Service Road From Ge 105 To Ge 123 | Surface Course Treatment | B | 2025-09-29 | 2025-10-06 | 8
1098163 | Regency Walk | Sutton Four Oaks | Regency Walk From Rosemary Hill Rd To End | Surface Course Treatment | A | 2025-10-01 | 2025-10-03 | 3
1085762 | Walmley Ash Road | Sutton Walmley & Minworth | Walmley Ash Road-Walmley Rd To Rbt At Webster Way | Surface Course Treatment | B | 2025-10-02 | 2025-10-08 | 7
1099138 | Brooks Road | Sutton Wylde Green | Brooks Road Service Road From Opp 59 & 61 To End | Surface Course Treatment | A | 2025-10-02 | 2025-10-03 | 2
1100285 | Wheatmoor Rise | Sutton Roughley | Wheatmoor Rise From Vincent Road To End | Surface Course Treatment | A | 2025-10-07 | 2025-10-09 | 3
992835 | Chester Road North | Sutton Vesey | Chester Road North-Lhc Start Dual Cway To C/L Monmouth Drive | Surface Course Treatment | A | 2025-10-08 | 2025-10-15 | 8
1086153 | Monmouth Drive | Sutton Vesey | Monmouth Drive-Rbt At Stonehouse Rd To Somerville Rd | Surface Course Treatment & Binder Patches | B | 2025-10-10 | 2025-10-17 | 8
1099754 | Chestnut Road | Moseley | Chestnut Road From Church Road To Kingswood Road | Surface Course Treatment | B | 2025-10-13 | 2025-10-13 | 1
1085578 | Long Nuke Road | Bartley Green | Long Nuke Road-Roundabout At Woodcock Lane | Surface Course Treatment | A | 2025-10-14 | 2025-10-14 | 1
1098737 | York Street | Harborne | Wilford Grove Cul-De-Sac From Cheswood Drive To End | Surface Course Treatment | A | 2025-10-15 | 2025-10-15 | 1
1100376 | Wilford Grove | Sutton Walmley & Minworth | York Street From High Street To Greenfield Road | Surface Course Treatment | B | 2025-10-15 | 2025-10-15 | 1
993002 | West Boulevard | Quinton | West Boulevard-Rbt At Court Oak Rd To Rbt At Tennal Lane | Surface Course Treatment | B | 2025-10-16 | 2025-10-17 | 2
1099630 | Paddocks Green | Soho & Jewellery Quarter | Paddocks Green From Crabtree Rd To End | Surface Course Treatment | A | 2025-10-17 | 2025-10-20 | 4
992997 | Lickey Road | Rednal | Badon Covert - Cul De Sac From Northleach Avenue To End | Full Depth Resurfacing | A | 2025-10-20 | 2025-10-24 | 5
1099204 | Badon Covert | Druids Heath & Monyhull | Lickey Road-Lhc Rbt At Bristol Rd South To End Of Dual Cway | Surface Course Treatment | B | 2025-10-20 | 2025-10-24 | 5
1099276 | Holborn Hill | Nechells | Ashwater Drive - Pennyacre Rd - End At Cl House Number 29/31 | Surface Course Treatment | A | 2025-10-20 | 2025-10-21 | 2
1099397 | Ashwater Drive | Druids Heath & Monyhull | Holborn Hill-Thimble Mill Lane To Lichfield Road | Surface Course Treatment | A | 2025-10-20 | 2025-10-24 | 5
1099099 | St James Road | Sutton Mere Green | St James Road From Mere Green Road To Tower Road | Surface Course Treatment | B | 2025-10-21 | 2025-10-24 | 4
992798 | Station Road | Yardley East | Mere Green Road-Rbt At Lichfield Rd To C/L Little Sutton La | Surface Course Treatment | B | 2025-10-23 | 2025-11-06 | 15
1085339 | Mere Green Road | Sutton Mere Green | Station Road-C/L Of Rlwy Bridge To C/L Of Bordesley Green E | Surface Course Treatment | B | 2025-10-23 | 2025-11-03 | 12
1099319 | Wheelers Lane | Brandwood & Kings Heath | West Heath Road Service Road From O/S No.149 To O/S No.167 | Surface Course Treatment | B | 2025-11-03 | 2025-11-04 | 2
1100468 | West Heath Road | Longbridge & West Heath | Wheelers Lane Service Road From Opp No.95 To O/S No.82 | Surface Course Inlay | A | 2025-11-03 | 2025-11-14 | 12
1157637 | Pype Hayes Road | Pype Hayes | Pype Hayes Road Roundabout At Pype Hayes Close | Surface Course Treatment | A | 2025-11-03 | 2025-11-03 | 1
1085944 | Wharfdale Road | Tyseley & Hay Mills | Wharfdale Road-C/L Of Kings Rd To Stockfield Road | Surface Course Treatment | B | 2025-11-13 | 2025-11-21 | 9
1085407 | Frankley Beeches Road | Frankley Great Park | Frankley Beeches Road-Egghill Rd Rbt To C/L Hollymoor Way | Full Depth Resurfacing | B | 2025-11-14 | 2025-11-21 | 8
1086209 | Bromford Road | Bromford & Hodge Hill | Bromford Road-Bromford Lane To Coleshill Road | Surface Course Treatment | B | 2025-11-19 | 2025-12-09 | 21
1100017 | Sunningdale Close | Handsworth Wood | Sunningdale Close From Craythorne Av To End At No 57 | Surface Course Treatment | B | 2025-11-20 | 2025-12-02 | 13
1085544 | Springfield Road | Moseley | Springfield Road-Rbt At School Rd To Rbt At Billesley La | Surface Course Treatment | B | 2025-11-21 | 2025-12-03 | 13
1099397 | Berkeley Road East | Tyseley & Hay Mills | West Heath Road Service Road From O/S No.149 To O/S No.167 | Surface Course Treatment | B | 2025-11-28 | 2025-12-08 | 11
1085223 | Worcester Lane | Sutton Roughley | Berkeley Road East-Berkeley Rd To C/L Fast Pits Rd | Surface Course Treatment | B | 2025-12-05 | 2025-12-19 | 15
1086348 | Newbury Road | Newtown | Edgbaston Road-Russell Rd Rbt To C/L River Rea Bridge | Surface Course Treatment | C | 2025-12-08 | 2025-12-10 | 3
992914 | Church Road | Edgbaston | Worcester Lane From Grange Lane To Roundabout At Harvest Fields Way | Surface Course Treatment | B | 2025-12-09 | 2025-12-11 | 3
1086030 | Charles Road | Small Heath | Charles Road-Coventry Road To Green Lane | Surface Course Treatment | B | 2025-12-09 | 2025-12-16 | 8
993024 | Fox Hollies Road | Acocks Green | Fox Hollies Road-Warwick Road To Rbt At Westley Road | Surface Course Treatment | B | 2026-01-05 | 2026-01-12 | 8
1157328 | Elkington Street | Newtown | Cuckoo Road-Lhc Rbt At Watson Rd To Heartlands Parkway Rbt | Surface Course Treatment | B | 2026-01-05 | 2026-01-12 | 8
992901 | Cuckoo Road | Nechells | Brook Lane Service Road From O/S No.345 To End Adj No.229 | Surface Course Treatment | B | 2026-01-07 | 2026-01-12 | 6
992967 | Coventry Road (Holder Road) | Tyseley & Hay Mills | Garland Street From Garrison St To End | Surface Course Treatment | A | 2026-01-12 | 2026-01-16 | 5
992976 | Watery Lane Middleway | Bordesley & Highgate | Moor Green Lane-Lhc Start Of Dual Cway To End Of Dual Cway | Surface Course Treatment | A | 2026-01-12 | 2026-01-20 | 9
992817 | Warwick Road | Acocks Green | Coventry Road-Lhc C/L Holder Rd To C/L Berkeley Rd | Surface Course Treatment | B | 2026-01-13 | 2026-01-21 | 9
992840 | Aldridge Road | Perry Barr | Parsons Hill-C/L Canal Bridge To Rbt At Monyhull Hall Rd | Surface Course Treatment | B | 2026-01-13 | 2026-01-19 | 7
992900 | Cuckoo Road | Nechells | Elkington Street From Miller St To Newtown Middleway | Surface Course Treatment | C | 2026-01-13 | 2026-01-19 | 7
1086306 | Holder Road | South Yardley | Warwick Road - From Rbt At Acocks Green To C/L Of Gospel Lane | Full Depth Resurfacing | B | 2026-01-13 | 2026-01-20 | 8
992779 | Bristol Road | Bournville & Cotteridge | Holder Road-Coventry Road To C/L Fast Pits Road | Surface Course Treatment | B | 2026-01-16 | 2026-01-19 | 4
1086308 | St Michaels Hill | Soho & Jewellery Quarter | Cuckoo Road-Rbt At Watson Road To Lichfield Road | Surface Course Treatment | B | 2026-01-16 | 2026-01-21 | 6
1099423 | Mountfield Close | Highters Heath | St Michaels Hill-C/L Of South Road To C/L Of Ashwin Road | Surface Course Treatment | B | 2026-01-19 | 2026-01-21 | 3
1100072 | Comberton Road | Garretts Green | Comberton Road Service Road From Opp 6 To End At No 11A | Surface Course Treatment | A | 2026-01-19 | 2026-01-21 | 3
992839 | Aldridge Road | Perry Barr | Bakers Lane-Rbt At Queslett Rd East To Sutton Oak Rd | Surface Course Treatment | C | 2026-01-20 | 2026-01-22 | 3
992951 | Bristol Road | Weoley & Selly Oak | Bristol Road- C/L Weoley Park Rd To C/L Of Oak Tree La | Full Depth Resurfacing | C | 2026-01-20 | 2026-02-22 | 34
1085465 | Great Barr Street | Bordesley & Highgate | Parsons Hill-C/L Canal Bridge To Rbt At Monyhull Hall Rd | Surface Course Treatment | B | 2026-01-20 | 2026-01-23 | 4
993012 | Walsall Road | Perry Barr | Great Barr Street-Heath Mill La To Rbt At Lawley Middleway | Surface Course Treatment | B | 2026-01-21 | 2026-01-21 | 1
992811 | Kingsbury Road | Sutton Walmley & Minworth | Kingsbury Road-Junct At Tyburn Rd To Rbt At Chester Rd | Full Depth Resurfacing | C | 2026-01-22 | 2026-01-30 | 9
992935 | Walsall Road | Perry Barr | Walsall Road From C/L Beeches Rd To Junct Old Walsall Rd | Surface Course Treatment | B | 2026-01-22 | 2026-01-22 | 1
993035 | Warwick Road | Acocks Green | Newtown Middleway-Lhc New Town Row To Dartmouth Circus | Surface Course Treatment | B | 2026-01-22 | 2026-02-03 | 13 | bar: #REF! to #REF!
1085458 | Factory Road | Soho & Jewellery Quarter | Kingsbury Road- East Bd-Start Of Dual Cway To City Boundary | Surface Course Treatment | C | 2026-01-22 | 2026-01-28 | 7
1099603 | Lawford Grove | Hodge Hill | Factory Road-C/L Of Ashwin Road To Park Road | Surface Course Treatment | B | 2026-01-22 | 2026-01-26 | 5
993013 | Walsall Road | Perry Barr | Walsall Road From C/L Of Rocky Lane To C/L Of Beeches Road | Surface Course Treatment | B | 2026-01-23 | 2026-01-26 | 4
993074 | Aldridge Road | Oscott | College Road-Springfield Rd Rbt To Rbtat Wake Green Rd | Surface Course Treatment | B | 2026-01-23 | 2026-02-04 | 13
992912 | Wake Green Road | Moseley | Bristol Road-Lhc C/L Of Oak Tree La To C/L Weoley Park Rd | Full Depth Resurfacing | C | 2026-01-25 | 2026-01-31 | 7
992882 | Jennens Road | Ladywood | Bacchus Road-Benson Road To Lodge Road | Surface Course Treatment | B | 2026-01-26 | 2026-01-28 | 3
992971 | Chester Road | Pype Hayes | Walsall Road-Lhc C/L Of Rocky Lane To C/L Of Perry Avenue | Surface Course Treatment | B | 2026-01-26 | 2026-01-28 | 3
1086071 | Bacchus Road | Soho & Jewellery Quarter | Chester Road-Start Of Dual Cway To Rbt Heartlands Spine Rd | Surface Course Treatment | B | 2026-01-26 | 2026-02-03 | 9
1085597 | Bakers Lane | Sutton Vesey | Jennens Road Slip Rd From The Priory Queensway To Jennens Road | Surface Course Treatment | B | 2026-01-27 | 2026-02-06 | 11
993054 | Coventry Road | Bordesley & Highgate | Coventry Road- Bordesley Circus To Camp Hill | Surface Course Treatment | B | 2026-01-29 | 2026-02-01 | 4
992959 | Tyburn Road | Pype Hayes | Kent Street From Wrentham St To Hurst St | Surface Course Treatment | B | 2026-02-02 | 2026-02-02 | 1
993057 | College Road | Sparkhill | Aldridge Road-Start Of Dual Cway To C/L Of Church Rd | Surface Course Treatment | C | 2026-02-02 | 2026-02-04 | 3
1098396 | Kent Street | Bordesley & Highgate | Tyburn Road Out Of City Slip Road From O/S No.900 Turning Right Onto Kingsbury Road | Surface Course Treatment | C | 2026-02-02 | 2026-02-05 | 4
992947 | Tyburn Road | Pype Hayes | Tyburn Road-Lhc From Kingsbury Road To C/L Of Bromford Lane | Surface Course Treatment | C | 2026-02-03 | 2026-02-12 | 10
992928 | Aldridge Road | Oscott | Witton Lane-Aston Hall Road To End Of Dual Cway | Surface Course Treatment | B | 2026-02-05 | 2026-02-13 | 9
1085658 | Hurst Lane | Shard End | Hurst Lane-Packington Avenue To Start Of Dual Cway | Surface Course Treatment | B | 2026-02-06 | 2026-02-13 | 8
993060 | Edgbaston Road | Balsall Heath West | Bradford Street -Barford Street To Moat Lane | Surface Course Treatment | B | 2026-02-08 | 2026-02-13 | 6
993018 | East Meadway | Glebe Farm & Tile Cross | Aldridge Road-Lhc College Rd At Mway Bri To C/L Church Rd | Surface Course Treatment | C | 2026-02-09 | 2026-02-12 | 4
992945 | Kingsbury Road | Pype Hayes | Lawford Grove From Gooch St To Start Of Garage Area | Full Depth Resurfacing | B | 2026-02-10 | 2026-02-19 | 10
1100018 | Weeford Drive | Handsworth Wood | Newbury Road-C/L Alma Street To High Street | Surface Course Treatment | B | 2026-02-12 | 2026-02-12 | 1
1100019 | Weeford Drive | Handsworth Wood | Church Road-Lhc Priory Rd Rbt To C/L Edgbaston Park Rd | Surface Course Treatment | A | 2026-02-13 | 2026-02-16 | 4
1085539 | Moor Green Lane | Moseley | Watery Lane Middleway-Lhc Garrison La Rbt Tobordesley Circus | Surface Course Treatment | B | 2026-02-16 | 2026-02-16 | 1
992986 | Newtown Middleway | Newtown | Mountfield Close From Junction Opp No 11 To End At No 18 | Surface Course Treatment | A | 2026-02-16 | 2026-02-18 | 3
1085536 | Moor Green Lane | Moseley | Duddeston Mill Road-Melvina Road To C/L Little Hall Road | Surface Course Treatment | A | 2026-02-16 | 2026-02-23 | 8
992899 | Witton Lane | Aston | Margaret Grove From Parkhill Road To Ravenhurst Road | Surface Course Treatment | B | 2026-02-17 | 2026-02-20 | 4
1099989 | Thetford Road | Perry Barr | Perry Wood Road From Booths Farm Rd To Calshott Rd | Surface Course Treatment | B | 2026-02-17 | 2026-02-25 | 9
1085918 | Duddeston Mill Road | Nechells | Weeford Drive Cul-De-Sac From No 27 To End At No 17 | Surface Course Treatment | A | 2026-02-19 | 2026-02-19 | 1
1098375 | Garland Street | Bordesley & Highgate | Richmond Road-C/L Yardley Green Rd To Bordesley Green East | Surface Course Treatment | B | 2026-02-20 | 2026-02-28 | 9
1085709 | Richmond Road | Yardley West & Stechford | Warwick Road-C/L Of Fox Hollies Rd To C/L Of Dudley Park Rd | Surface Course Treatment | B | 2026-02-22 | 2026-02-25 | 4
1085899 | Bradford Street | Bordesley & Highgate | East Meadway-C/L Kitts Green Rd To C/L Tile Cross Rd | Surface Course Treatment & Binder Patches | B | 2026-02-22 | 2026-02-24 | 3
992838 | Tamworth Road | Sutton Trinity | Wood Lane Service Road From Ge 111 To Ge 161 | Full Depth Resurfacing | B | 2026-02-23 | 2026-02-23 | 1
993008 | Kingstanding Road | Oscott | Merritts Brook Lane-Rbt At Holloway To Rbt At Basil Road | Full Depth Resurfacing | C | 2026-02-23 | 2026-03-11 | 17
1157644 | Wood Lane | Pype Hayes | Kingstanding Road-Lhc College Rd To Rbt At Kings Road | Surface Course Treatment | C | 2026-02-24 | 2026-03-04 | 9
1099974 | Perry Wood Road | Perry Barr | Wood Lane From Rbt At Fort Service Rd To Rbt At Holly Lane | Surface Course Treatment | C | 2026-02-24 | 2026-03-06 | 11
1085715 | St Margarets Road | Ward End | Walsall Road-Rosemary Hill Rd To C/L Streetly Lane | Surface Course Treatment & Binder Patches | B | 2026-02-24 | 2026-03-04 | 9
1099908 | Dormington Road | Oscott | Aldridge Road-Rbt At Queslett Rd To C/L Of Booths Lane | Surface Course Treatment | C | 2026-02-25 | 2026-02-27 | 3
1100478 | Brook Lane (Service Road) | Billesley | Weeford Drive From Hamstead Hall Road To End At No 32 | Surface Course Treatment | B | 2026-02-26 | 2026-02-26 | 1
1098974 | Southbourne Avenue | Bromford & Hodge Hill | Flaxley Road From Cl Church Ln To Audley Road | Surface Course Treatment | B | 2026-03-03 | 2026-03-05 | 3
1085415 | Merritts Brook Lane | Allens Cross | Knights Road-Warwick Rd To C/L Tynedale Rd | Surface Course Treatment | A | 2026-03-03 | 2026-03-13 | 11
1086261 | Tynedale Road | Hall Green North | St Margarets Road-Washwood Heath Rd To Bromford La | Surface Course Treatment | B | 2026-03-05 | 2026-03-20 | 16
1098823 | Wood Lane | Handsworth Wood | Dormington Road From Wandsworth Rd To Lambeth Road | Surface Course Treatment | B | 2026-03-05 | 2026-04-01 | 28
1086249 | Knights Road | Tyseley & Hay Mills | Marsh Hill-Lhc C/L Of George Road To Bleak Hill Road | Surface Course Treatment | B | 2026-03-05 | 2026-03-05 | 1
1099704 | Margaret Grove | Harborne | Rednal Road From Rbt At Redhill Road To Westhill Road | Full Depth Resurfacing | C | 2026-03-09 | 2026-03-11 | 3
1099074 | Bromwich Drive | Sutton Trinity | Thetford Road From Foden Road To Turnberry Road | Surface Course Treatment | B | 2026-03-10 | 2026-03-11 | 2
993046 | Walsall Road | Sutton Four Oaks | Wake Green Road-C/L Yardley Wood Rd To C/L Church Rd | Full Depth Resurfacing | C | 2026-03-11 | 2026-03-20 | 10
992864 | Heartlands Parkway | Nechells | Nechells Parkway-C/L Of Rupert St To C/L Bloomsbury St | Surface Course Treatment | B | 2026-03-12 | 2026-03-17 | 6
1085631 | Streetly Road | Stockland Green | Streetly Road-Dual Cway-Reservoir Rd To Short Heath Rd | Surface Course Treatment | B | 2026-03-12 | 2026-03-26 | 15
992867 | Nechells Parkway | Nechells | Tamworth Road-C/L Bedford Rd To Dual Cway Near Bromwich Dr | Surface Course Treatment & Binder Patches | C | 2026-03-17 | 2026-03-23 | 7
992865 | Heartlands Parkway | Nechells | Heartlands Parkway-Lhc Rbt At Bromford La To Cuckoo Rd Rbt | Surface Course Treatment | B | 2026-03-18 | 2026-03-23 | 6
992965 | Alcester Road South | Highters Heath | Alcester Road South- Warstock Lane to Maypole La Rbt | Full Depth Resurfacing | C | 2026-03-22 | 2026-03-30 | 9
1098163 | Rednal Road | Kings Norton North | Aldridge Road-C/L Of Booths Lane To College Road | Surface Course Treatment | C | 2026-03-24 | 2026-03-31 | 8
992960 | Marsh Hill | Stockland Green | Tynedale Road-Olton Boulevard West To C/L Spring Road | Full Depth Resurfacing | C | 2026-03-24 | 2026-03-27 | 4
1158086 | Flaxley Road | Glebe Farm & Tile Cross | Cole Hall Lane-Kitts Green Rd Rbt To C/L Bushbury Rd | Surface Course Treatment | B | 2026-03-25 | 2026-03-27 | 3
992919 | Parsons Hill | Kings Norton North | Moor Green Lane-Shutlock La To C/L River Rea Bridge | Surface Course Treatment | B | 2026-03-30 | 2026-03-31 | 2
1086298 | Cole Hall Lane | Glebe Farm & Tile Cross | Southbourne Avenue From Stechford Road To Coleshill Road | Surface Course Treatment | B | 2026-03-30 | 2026-04-03 | 5

## Footways IIP
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions.
Footways IIP Programme
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [8 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
[9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05
| Task ID | Task Name | Ward | Scheme Extents | Treatment | START | END | DAYS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| OWPFW9 | Coventry Road | Tyseley & Hay Mills | Coventry Road-C/L Kings Rd To C/L Berkeley Rd | Bitumen | 2025-09-01 | 2025-09-06 | 6
| OWPFW8 | Coventry Road | Tyseley & Hay Mills | Coventry Road-Heybarnes Circus Rbt To C/L Kings Rd | Bitumen | 2025-09-09 | 2025-09-23 | 15
| OWPFW14 | Presthope Road | Weoley & Selly Oak | Presthope Road From Opp No 172 Swarthmore Road To Opp No 74 | Bitumen | 2025-09-18 | 2025-10-23 | 36
| OWPFW19 | Stechford Road | Bromford & Hodge Hill | Stechford Road-Stechford Lane To Rbt At Coleshill Road | Bitumen | 2025-09-22 | 2026-03-06 | 166
| OWPFW6 | Wetherfield Road | Tyseley & Hay Mills | Wetherfield Road From Mayfield Road To Cl Briarfield Road | Bitumen | 2025-09-22 | 2025-10-22 | 31
| OWPFW20 | Church Lane | Glebe Farm & Tile Cross | Church Lane -C/L Of Flaxley Road To Kitts Green Road | Bitumen | 2025-10-13 | 2026-01-15 | 95
| OWPFW5 | Rednal Road | Longbridge & West Heath | Rednal Road From Rbt At Redhill Road To Westhill Road | Bitumen | 2025-10-20 | 2026-02-01 | 105
| OWPFW21 | Wyche Avenue | Brandwood & King's Heath | Wyche Avenue From Brandwood Rd To End | Bitumen | 2025-10-21 | 2025-11-24 | 35
| OWPFW7 | Victoria Road | Aston | Victoria Road-Rbt At Witton Road To Park Circus | Bitumen | 2025-11-24 | 2025-12-19 | 26
| OWPFW23 | Lea Ford Road | Glebe Farm & Tile Cross | victoria Road-Rbt At Witton Road To Park Circus | Bitumen | 2025-11-24 | 2026-03-03 | 100
| OWPFW17 | Riddfield Road | Bromford & Hodge Hill | Riddfield Road From Chipperfield Road To Kempson Road | Bitumen | 2026-01-05 | 2026-02-18 | 45
| OWPFW11 | Broughton Crescent | Northfield | Broughton Crescent From Bf Bristol Rd W To Bf Bristol Rd E | Bitumen | 2026-01-12 | 2026-02-02 | 22
| OWPFW4 | Navigation Street | Ladywood | Whole Road | Block Paving | 2026-01-19 | 2026-03-09 | 50
| OWPFW10 | Cliff Rock Road | Rubery & Rednal | Cliff Rock Road From Edgewood Road To Leach Green Lane | Bitumen | 2026-02-02 | 2026-03-06 | 33
| OWPFW12 | Edgehill Road | Longbridge & West Heath | Edgehill Road From Adj To 252 Fairfax Rd To Fairfax Rd | Bitumen | 2026-02-12 | 2026-03-31 | 48

## ELV Traffic Signals IIP
Create a Project Schedule in this worksheet Enter title of this project in cell B1 Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet Continue navigating down column A to hear further instructions
ELV Traffic Signals IIP Programme
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4 The project start date is considered Week 1 To change the display week, simply enter a new week number in cell E4 The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated There are 8 weeks represented in this view from cell I4 through cell BF4 You should not modify these cells Display Week: label is in cell C4 | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
[7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03
| Task ID | Task Name | Ward | START | END | DAYS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
| E4662 - E4663 | Kings Road / Banners Walk | Kingstanding | 2025-09-22 | 2025-09-22 | 1
| E1537 | Bells Lane / Brockworth Road | Druids Heath & Monyhull | 2025-09-24 | 2025-09-24 | 1
| E1937 | Hobmoor Road / Starbank Road | Small Heath | 2025-09-26 | 2025-09-26 | 1
| E2224 | Stechford Lane / Stechford Road | Bromford & Hodge Hill | 2025-09-29 | 2025-09-30 | 2
| E1206 | Pershore Road / Riverside Drive | Bournbrook & Selly Park | 2025-10-01 | 2025-10-01 | 1
| E2252 | Washwood Heath Road / Chetwynd Road | Ward End | 2025-10-03 | 2025-10-03 | 1
| E1949 | Charles Road / Somerville Road | Small Heath | 2025-10-06 | 2025-10-06 | 1
| E1159 | Westbourne Rd Nr St Georges Close | Edgbaston | 2025-10-08 | 2025-10-08 | 1
| E1417 | Linden Road / Woodbrooke Road | Bournville & Cotteridge | 2025-10-10 | 2025-10-10 | 1
| E2529 | Victoria Road / Upper Sutton Street | Aston | 2025-10-15 | 2025-10-16 | 2
| E4243 | Lichfield Rd nr Barker Rd | Sutton Four Oaks | 2025-10-17 | 2025-10-17 | 1
| E1394 | Chester Road / Jaguar Works Exit / Retail Park Exit | Castle Vale | 2025-10-20 | 2025-10-23 | 4
| E0321 | Old Snow Hill/ Summer Lane | Newtown | 2025-10-27 | 2025-10-28 | 2
| E1426 | Umberslade Road / Pershore Road | Bournbrook & Selly Park | 2025-10-29 | 2025-10-29 | 1
| E0136 - E0137 | The Priory Queensway / Old Square | Ladywood | 2025-10-30 | 2025-10-30 | 1
| E0145 | Corporation St nr Priory Queensway | Ladywood | 2025-10-30 | 2025-10-30 | 1
| E1401 | Longbridge Lane / Devon Way | Longbridge & West Heath | 2025-11-04 | 2025-11-07 | 4
| E1375 | Bristol Rd South / Frankley Beeches Rd | Allens Cross | 2025-11-10 | 2025-11-13 | 4
| E1321 | Bristol Rd S / Church Rd / Bell Lane | Northfield | 2025-11-17 | 2025-11-18 | 2
| E0407 | New Town Row / Brewery St | Newtown | 2025-11-19 | 2025-11-19 | 1
| E2824 | Holyhead Rd nr Park Lane | Handsworth Wood. | 2025-11-24 | 2025-11-24 | 1
| E2833 | Rookery Rd nr Mervyn Rd | Handsworth | 2025-11-24 | 2025-11-24 | 1
| E1374 | Bristol Road South / Great Stone Road | Northfield | 2025-11-25 | 2025-11-28 | 4
| E4111 | Birmingham Rd nr Maney Hill Rd | Sutton Trinity. | 2025-11-25 | 2025-11-25 | 1
| E4124 | Jockey Rd nr Goldeslie Rd | Sutton Wylde Green. | 2025-11-25 | 2025-11-25 | 1
| E4512 | Chester Rd nr Green Lane | Sutton Wylde Green | 2025-11-26 | 2025-11-26 | 1
| E4514 | Birmingham Rd nr Penns Lane | Sutton Wylde Green | 2025-11-26 | 2025-11-26 | 1
| E4528 | Sutton New Rd nr Barnabus Rd I/Bd | Erdington | 2025-11-27 | 2025-11-27 | 1
| E4529 | Sutton New Rd nr Barnabus Rd O/Bd | Erdington | 2025-11-27 | 2025-11-27 | 1
| E4530 | Gravelly Hill nr Kingsbury Rd | Gravelly Hill. | 2025-11-28 | 2025-11-28 | 1
| E0330 - E0331 | Icknield St nr Park Rd | Soho & Jewellery Quarter | 2025-12-01 | 2025-12-01 | 1
| E4532 | Chester Rd nr Church Rd | Sutton Vesey. | 2025-12-01 | 2025-12-01 | 1
| E4535 | Station Rd nr Osborne Rd | Erdington | 2025-12-01 | 2025-12-01 | 1
| E4554 | High St Erdington nr Six Ways | Gravelly Hill. | 2025-12-02 | 2025-12-02 | 1
| E4557 | Reservoir Rd nr Summer Rd | Gravelly Hill. | 2025-12-03 | 2025-12-03 | 1
| E4619 | Hawthorn Rd nr Warren Rd | Kingstanding | 2025-12-03 | 2025-12-03 | 1
| E4436 | Tyburn Rd nr Wheelwright Rd O/Bd | Gravelly Hill. | 2025-12-04 | 2025-12-04 | 1
| E0638 | Camp Hill nr Sandy Lane O/Bd | Bordesley & Highgate. | 2025-12-08 | 2025-12-08 | 1
| E0639 | Camp Hill nr Sandy Lane I/Bd | Bordesley & Highgate. | 2025-12-08 | 2025-12-08 | 1
| E0647 | Bradford St nr Moseley Rd | Bordesley & Highgate. | 2025-12-09 | 2025-12-09 | 1
| E1215 | Edgbaston Park Rd nr University Rd | Edgbaston | 2025-12-09 | 2025-12-09 | 1
| E1219 | Edgbaston Park Rd nr Somerset Rd | Edgbaston | 2025-12-10 | 2025-12-10 | 1
| E1220 | Pritchatts Rd nr Edgbaston Park Rd | Edgbaston | 2025-12-10 | 2025-12-10 | 1
| E2842 | Hamstead Hill nr Cherry Orchard Rd | Handsworth Wood. | 2025-12-11 | 2025-12-11 | 1
| E2619 | Lozells Road / Wheeler Street | Lozells | 2025-12-11 | 2025-12-11 | 1
| E1245 | Bristol Rd S nr Griffins Brook Lane O/Bd | Bournville & Cotteridge. | 2025-12-12 | 2025-12-12 | 1
| E1943 | Coventry Rd / Muntz St / Golden Hillock Rd | Bordesley Green | 2025-12-15 | 2025-12-17 | 3
| E1246 | Bristol Rd S nr Griffins Brook Lane I/Bd | Bournville & Cotteridge. | 2025-12-19 | 2025-12-19 | 1
| E2832 | Handsworth Wood Rd nr Devonshire Rd | Handsworth Wood. | 2026-01-05 | 2026-01-05 | 1
| E4553 | Gravelly Hill North nr Fentham Rd | Gravelly Hill. | 2026-01-06 | 2026-01-06 | 1
| E1422 | Pershore Rd nr Umberslade Rd | Bournbrook & Selly Park | 2026-01-07 | 2026-01-07 | 1
| E1539 | Druids Lane nr Crabmill Lane | Druids Heath & Monyhull | 2026-01-07 | 2026-01-07 | 1 | bar: #REF! to #REF!
| E1936 | Bordesley Green Rd nr Belchers Lane | Heartlands | 2026-01-08 | 2026-01-08 | 1
| E1990 | Coventry Rd nr Watt's Rd | Bordesley Green | 2026-01-08 | 2026-01-08 | 1
| E1133 | Harborne High St nr Serpentine Rd | Harborne | 2026-01-12 | 2026-01-12 | 1
| E1134 | Harborne Park Rd nr Harborne High St | Harborne | 2026-01-13 | 2026-01-13 | 1
| E1538 | Alcester Rd S nr Glenavon Rd | Druids Heath & Monyhull | 2026-01-14 | 2026-01-14 | 1
| E1722 | Stratford Rd nr Cambrai Dr | Hall Green North | 2026-01-15 | 2026-01-15 | 1
| E1727 | Stratford Rd nr Green Hill Way N'Bd | Hall Green North | 2026-01-15 | 2026-01-15 | 1
| E1822 | Stratford Rd nr Green Bank Av | Hall Green North | 2026-01-16 | 2026-01-16 | 1
| E2728 | Dudley Road nr Cavendish Road | North Edgbaston | 2026-01-19 | 2026-01-19 | 1
| E2722 | Dudley Rd nr Winson St | North Edgbaston | 2026-01-19 | 2026-01-19 | 1
| E1964 | Coventry Rd nr Gladys Rd O/Bd | Tyseley & Hay Mills | 2026-01-20 | 2026-01-20 | 1
| E1963 | Coventry Rd nr Gladys Rd I/Bd | Bordesley Green | 2026-01-20 | 2026-01-20 | 1
| E2121 | Meadway nr Mirfield Rd | Glebe Farm & Tile Cross | 2026-01-21 | 2026-01-21 | 1
| E2129 | Garretts Green Lane nr Horrell Rd | Yardley East | 2026-01-21 | 2026-01-21 | 1
| E2216 | Bromford Drive nr Reynoldstown Rd | Bromford & Hodge Hill | 2026-01-22 | 2026-01-22 | 1
| E2258 | Washwood Heath Rd nr Sladefield Rd | Ward End | 2026-01-22 | 2026-01-22 | 1
| E2928 | Old Walsall Rd nr Rocky Ln | Perry Barr | 2026-01-23 | 2026-01-23 | 1
| E4454 | Tyburn Rd nr Abbots Rd 0/Bd | Gravelly Hill | 2026-01-23 | 2026-01-23 | 1
| E1517 | Wake Green Rd nr Grove Ave | Moseley | 2026-01-26 | 2026-01-26 | 1
| E1648 | Baker St nr Warwick Rd | Sparkbrook & Balsall Heath East | 2026-01-26 | 2026-01-26 | 1
| E4552 | Gravelly Hill North nr Wheelwright Rd | Gravelly Hill. | 2026-01-27 | 2026-01-28 | 2
| E4527 | Wood End Road nr Six Ways, Erdington | Erdington | 2026-01-27 | 2026-01-27 | 1
| E1364 | Bristol Rd S nr Ashill Rd I/Bd | Rubery & Rednal | 2026-01-28 | 2026-01-29 | 2
| E1385 | New Inns Lane nr Reaside School | Frankley Great Park | 2026-01-28 | 2026-01-29 | 2
| E1531 | Maypole Lane nr Westfield Ave | Highter's Heath | 2026-01-29 | 2026-01-29 | 1

## Full Traffic Signals IIP
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions.
Full Traffic Signals IIP Programme
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
[7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03
| Task ID | Task Name | Ward | START | END | DAYS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
| E4116 | High St nr Railway Road | Sutton Trinity | 2025-09-01 | 2025-09-10 | 10
| E0736/7 | Highgate Middleway | Sparkbrook & Balsall Heath East | 2025-10-27 | 2025-11-12 | 17
| E0170 | Snow Hill Queensway / St Chads | Ladywood | 2026-03-02 | 2026-03-10 | 9
| E2231 | Washwood Heath Road / Bromford Lane | Bromford & Hodge Hill | 2026-03-09 | 2026-05-18 | 71
| E2611 | Soho Hill / Hamstead Road | Soho & Jewellery Quarter | 2026-02-02 | 2026-05-01 | 89
| E2111 | Coventry Road / Sheaf Lane | Sheldon
| E0711 | Belgrave Street / Longmore Street | Bordesley & Highgate

## Winter Sensors IIP
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions.
Full Traffic Signals IIP Programme
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01
[7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07
| Task ID | Task Name | Ward | START | END | DAYS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| LFR- WS | Lichfield Road | Sutton Coldfield | 2025-11-24 | 2025-11-24 | 1
| CVR-WS | Coventry Road/Forest Road | South Yardley | 2025-11-25 | 2025-11-25 | 1
| SNL-WS | Shenley Lane | Allens Cross | 2025-11-26 | 2025-11-26 | 1
| RDR-WS | Redditch Road | Longbridge & West Heath | 2025-11-26 | 2025-11-26 | 1
| HRW-WS | Hagley Road West | Quinton | 2025-11-27 | 2025-11-27 | 1
| KBR-WS | Kingsbury Road | Tyburn | 2025-11-28 | 2025-11-28 | 1

## LED Street Lighting IIP
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions.
LED Street Lighting IIP Programme
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [7 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
[8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03
| Task ID | Task Name | Ward | No of Columns | START | END | DAYS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
| 2700163 | Hagley Road West (SNAGS) | Quinton | 1 | 2025-01-22 | 2025-01-22 | 1
| 2700072 | Bristol Road South | Northfield | 80 | 2025-10-08 | 2025-10-09 | 2
| 2703832 | Bristol Road | Selly Oak | 20 | 2025-10-13 | 2025-10-13 | 1
| 2735928 | Bristol Road 2 | Edgbaston | 25 | 2025-10-14 | 2025-10-15 | 2
| 2735823 | Bristol Road South 2 | Northfield | 143 | 2025-10-15 | 2025-10-16 | 2
| 2735823 | Bristol Road South 2 | Northfield | 143 | 2025-10-20 | 2025-10-23 | 5
| 2701741 | Hagley Road 1 & 2 & 3 | Edgbaston | 71 | 2025-10-27 | 2025-10-30 | 4
| 2735823 | Bristol Road South 2 (2) | Northfield | 143 | 2025-11-03 | 2025-11-06 | 4
| 2735823 | Bristol Road South 2 (3) | Northfield | 143 | 2025-11-10 | 2025-11-13 | 4
| 2735824 | Bristol Road South 3 | Northfield | 86 | 2025-11-19 | 2025-11-21 | 3
| 2708856 | Jockey Road | Sutton Vesey | 64 | 2025-11-24 | 2025-11-27 | 4
| 2700027 | Clarence Road | Sutton | 58 | 2025-12-01 | 2025-12-04 | 4
| 2701211 | Adderley Road | Hodge Hill | 14 | 2025-12-08 | 2025-12-08 | 1
| 2704726 | Brookvale Road | Perry Barr | 27 | 2025-12-08 | 2025-12-09 | 2
| 2700164 | Hagley Road West | Quinton | 101 | 2025-12-10 | 2025-12-11 | 2
| 2700164 | Hagley Road West | Quinton | 101 | 2025-12-16 | 2025-12-17 | 2
| 2700163 | Hagley Road West 2 | Quinton | 1 | 2025-12-18 | 2025-12-18 | 1
| 2735824 | Bristol Road South 3 | Northfield | 86 | 2026-01-05 | 2026-01-07 | 3
| 2701232 | Alma Street | Ladywood | 8 | 2026-01-12 | 2026-01-12 | 1
| 2704726 | Brookvale Road (SNAGS) | Perry Barr | 27 | 2026-01-12 | 2026-01-12 | 1
| 2701752 | Harborne Road | Edgbaston | 16 | 2026-01-13 | 2026-01-13 | 1
| 2701511 | Communication Row | City Centre | 4 | 2026-01-14 | 2026-01-14 | 1
| 2702506 | William Street | City Centre | 5 | 2026-01-14 | 2026-01-14 | 1
| 2701350 | Blucher Street | City Centre | 8 | 2026-01-14 | 2026-01-14 | 1
| 2708856 | Jockey Road (SNAGS) | Sutton Vesey | 64 | 2026-01-19 | 2026-01-19 | 1
| 2702411 | Upper Gough Street | City Centre | 6 | 2026-01-20 | 2026-01-20 | 1
| 2701458 | Chapmans Passage | City Centre | 3 | 2026-01-20 | 2026-01-20 | 1
| 2701692 | Gough Street | City Centre | 5 | 2026-01-20 | 2026-01-20 | 1
| 2702000 | Marshall Street | City Centre | 4 | 2026-01-20 | 2026-01-20 | 1
| 2701752 | Harborne Road | Edgbaston | 16 | 2026-01-21 | 2026-01-21 | 1
| 2735844 | Lordswood Road | Edgbaston | 6 | 2026-01-21 | 2026-01-21 | 1
| 2701741 | Hagley Road (SNAGS) | Edgbaston | 71 | 2026-01-22 | 2026-01-22 | 1
| 2700072 | Bristol Road South (SNAGS) | Northfield | 80 | 2026-01-22 | 2026-01-22 | 1
| 2703832 | Bristol Road (SNAGS) | Selly Oak | 20 | 2026-01-22 | 2026-01-22 | 1

## Overall IIP
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions.
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  |  |  | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | #REF! | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10
Structure No | Task Name | START | END | DAYS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Tunnels | 2025-06-30 | 2026-03-23 | 267
1 | Footway Resurfacing | 2025-09-01 | 2026-03-26 | 207
1 | Full Traffic Signal Refurbishments | 2025-09-01 | 2026-01-12 | 134
1 | ELV Traffic Signal Upgrades | 2025-09-22 | 2026-01-28 | 129
1 | Carriageway Resurfacing | 2025-09-29 | 2026-04-16 | 200
| LED Street Lighting Upgrades | 2025-10-08 | 2026-01-21 | 106
| Winter Sensors | 2025-11-24 | 2025-11-28 | 5

## Sheet1 (hidden)
BST - Task Order Tracking
Kier
Birmingham ISC
Supervisor | Job No | Job Description | Approx Start Date | Prices Required (3/1) | Hankinsons | Community Clean (CC) | R&C Williams | Haystouns | Nuweld | Fitgeralds | USL | VolkerLaser | Route One |  |  |  |  | Quotation Submitted Date | Task Order Received Date | Comments
CW | 3082 | Richard Street | 2022-04-25 | 3 | 6205 | 13831 | 6079 | [10 empty] | 2022-02-03 | 2022-02-25 | Hankinson Works
CW | 03024 | Winson Green Canal Bridge |  | 3 | 22195 | 15034.45 | 12115 | [10 empty] | 2022-02-21 | 2022-03-16 | CC Works
RC | 03050 | Curzon Street Canal Bridge | [5 empty] | 7785
RC | 03051 | Fazeley Street Canal | 2022-05-23 | 3 | 10234 | 25912.02 | 19250 | [10 empty] | 2022-02-22 | 2022-02-25 | Hankinson Works
CW | 03076 | Deykin Avenue Canal Bridge |  | 1 | Declined |  | 41000.12 | 39982 | [9 empty] | 2022-03-10 | 2022-03-18 | Haystoun Works
RC | 03083 | Cuckoo Road Canal Bridge |  |  | 55000 | Declined | 77880 | Declined | [10 empty] | 2022-02-25 | Hankinson Works
RC | 03635 | Aston Expressway Retaining Wall 16 |  |  | 27647 | 46726.28 | 29712 | [10 empty] | 2022-02-16 |  | Hankinson Works
CW | 03677 | Dartmouth Circus Wall H |  | 3 | 15158 | 21012.74 | 22500 | [10 empty] | 2022-02-03 | 2022-03-16 | CC Works
CW | 03679 | Dartmouth Circus Gyratory Wall West |  | 1 | 99275 | 337000 | 140433.75 | [12 empty] | Strengthening Scheme - On hold
RC | 03690 | Dartmouth Middleway | 2022-04-11 | 3 | 31786 | 48500 | 69500 | [12 empty] | Tarmac works - On hold
RC | 03802 | Woodbridge Road Railway Bridge |  |  | 8135 | 35147.7 | 26062.5 | [12 empty] | Hankinson Works
CW | 03811 | Reservoir Road Railway Footbridge |  | 3 | 9899 | 21795 | [13 empty] | Awaiting RCW Quote
RC | 03813 | Cartland Road Railway Bridge |  |  |  |  | 4103.89 | 1406 | 1850
RC | 03823 | Lichfield (Four Oaks) Railway Bridge
RC | 03833 | Esso Sidings Railway Bridge
CW | 04007 | Zig-Zag Footbridge |  | 3 |  |  |  | 13974.97
RC | 04032 | Bells Lane Culvert
RC | 04065 | Bristol Road South |  | 3
RC | 04113 | Hays Mills Old Bridge |  |  | Declined | 22279.7 | 3892 | 7540
RC | 04303 | Pershore Road Bridge | 2022-06-01 | 3
RC | 04431 | Westhill Road
RC | 04432 | Westhill Road Bridge |  | 3 | Declined | Declined | 7149.38 | 9860
RC | 04578 | Hurstwood Road Culvert | [17 empty] | On hold
CW | 04645 | Salford Bridge |  | 3 | [15 empty] | On hold
CW | 07502 | Rubery Flyover (Concrete) |  | 3 | [15 empty] | On hold
CW | 07604 | Lawley Middleway Bridge | 2022-05-23 | 3 | [15 empty] | On hold
RC | 07617E | Five Ways East Subway (Cleaning) | 2022-04-18 | 3 | [15 empty] | On hold
RC | 07617E | Five Ways East Subway (Drainage) | [17 empty] | On hold
CW | 07624 | Barrow Walk Subway (Cleaning) |  | 3 | [15 empty] | On hold
CW | 07625 | Barrow Walk Subway (Works) |  | 3 |  |  | 30147.19 | [12 empty] | On hold due to potential strenghtening works on main bridge.
RC | 07705A | Birchfield Southeast Road Bridge |  |  | 9063 | 8331 | 13950 | 9868 | [9 empty] | 2022-03-16 | 2022-04-01 | CC Works
RC | 07705B | Birchfield Northwest Road Bridge | [6 empty] | 881.38 | [8 empty] | 2022-03-10 |  | Nuweld Works
RC | 07705K | Birchfield Road West Retaining Wall |  |  |  |  | 2578.2 | 1775 | 1950 | [10 empty] | R&CW Works
RC | 07707 | Hatfield Rd Subway | 2022-06-06 | 3 |  |  | 964.2 | [12 empty] | R&CW Works
RC | 07708 | Trinity Flyover | 2022-05-01 | 3 |  |  | 4061.25 | 7418 | Declined | [10 empty] | Quotes to be updated
PW | 07708 | Trinity Flyover (Damaged Guttering) |  |  |  |  | 1243.73 | [12 empty] | Require 2 more Quotes
CW | 07712J | The Broadway Subway S7 |  | 1 |  |  | 10444.49 | 10890 | 14133.38 | [10 empty] | Complete
RC | 07712K | Birchfield Underpass SW Wall | [6 empty] | 1221.78 | [10 empty] | Nuweld Works
RC | 07712M | Birchfield Underpass NW Wall
RC | 07712P | Birchfield Underpass E Wall
RC | 07712Q | Birchfield Underpass NE Wall | [6 empty] | 9121.86 | [10 empty] | Change in scope back with DMcK
RC | 07804 | Aston Bridge B7 |  |  |  |  | 7965 | 1 | 1 | [10 empty] | Listed structure.
PW | 07804 | Aston Bridge B7 (Staircase Trial Holes) |  | 1 |  |  | 3819.38 | 11098 | 14853
FC | 07804 | Aston Brige parpet repair |  |  |  |  | 6980.63 | 7985 | 8100
RC | 07808 | Tame Valley Viaduct |  | 3 | [15 empty] | PCI Pack required for pricing form Pui Ho
RC | 07809C | Aston E/W A38M Gantry G3 | 2022-04-04 | 3 |  |  | 9677.81 | Declined | 1
PW | 07901C | Paradise Circus Footbridge |  |  |  |  | 21273.57 | 5495 | 5585.73
CW | 07905I | Dale End Bridge |  | 3 |  |  |  | 37247.3 | [11 empty] | V&G Works
RC | 07907A-P | Lancaster Circus Gyratory | 2022-05-09 | 3
PW | 07907C | Lancaster Flyover (Dameged Guttering)
RC | 07909D | Dudley Street Bridge | 2022-06-13 | [5 empty] | 19179.18 | [9 empty] | 2022-03-22 | Nuweld Works
CW | 07911C | Suffolk Street Viaduct | 2022-04-24 | 1 |  |  |  | 988 | [11 empty] | PCI Pack required for pricing form Pui Ho
CW | 07912 | Queens Way Tunnel |  | 3
CW | 0793C | St Chads Tunnel |  | 3
CW |  | Water Orton Lane Retaining Wall | 2022-04-24 | 3
AP |  | Paradise Lane | 2022-05-03 | 1 |  |  | 25050 | 25000 | 14000
|  |  |  | Total Priced Value | 294597 | 595569.89 | 597833.09 | 198313.27 | 90878.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total AWARDED value (to date) | 41987 | 84547.19 | 20967.52 | 39982 | 20060.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Works Awarded to